## Whangarei
Situation Report | [6 empty] | Name of Event: | Severe Weather Warning - 24/25 July 22
Local Authority Area: |  |  |  | Whangarei District Council
SitRep No. |  | 3 |  | (ref Page 235 Section SI02 - Incident Response)
Date: | 2022-07-25
Time: | 4PM |  |  | ( Daily SitReps due before 8am, 12noon and 4pm - or as agreed with the NTA Engineer's Rep)
Contract Area | Road Name | Route Position | Side | Site location description (eg. Xkm past Y road) | Date reported | Time | Source of Info (Contractor, call centre, public etc) | ROAD STATUS (see column 'w' notes) | Road Damage (see column 'v' notes) | RAMM Dispatch ID | Action Taken | Estimated Outage | Any planned action required | Date Resolved | Time Resolved | Additional Notes and Comments | Initial Response Cost | Claimed to date | Permanent repair cost
South | ONE TREE POINT RD | 4551 |  | Second Roundabout | 2022-07-25 | 7:00 | Call Centre | Road Passable - Caution Required | Fallen Tree |  | Crew going to check and clear |  |  | 2022-07-25 | 9:30
South | CULLEN RD | 2631 |  |  | 2022-07-24 | 12:00 | Call Centre | One Lane Only | Landslide - Overslip |  | Crew going to clear |  |  | 2022-07-25 | 10:00
South | MILL RD | TBC |  | Surface flooding city bound lane between Nixon st and Whareora Rd | 2022-07-25 | 6:45 | Contractor | Road Open | Surface water hazard |  | Crew checking grates
South | RUSSELL RD (CTL) | 474 |  |  | 2022-07-25 | 7:32 | Call Centre | Road Open | Fallen Tree |  | Tree cleared |  |  | 2022-07-25 | 10:27
South | CEMETERY RD | 150 |  |  | 2022-07-25 | 8:50 | Call Centre | Road Open | Fallen Tree |  | Tree will be cleared tomorrow, tree is clear of live lanes |  | tree will be cleared 26/7
South | BEACH RD | 900 |  |  | 2022-07-25 | 9:39 | Call Centre | Road Open | Fallen Tree |  | Crew attending |  | tree will be cleared by 130pm | 2022-07-25 | 12:59
South | WAIPU GORGE RD | 4801 |  | approx RP given, crews on their way | 2022-07-25 | 10:20 | Call Centre | Road Closed | Landslide - Overslip |  | Crew attending
South | CODLIN RD | TBC |  |  | 2022-07-25 | 12:15 | Public | Road Passable - Caution Required | Flooding
South | BROOKS RD | TBC |  |  | 2022-07-25 | 11:00 | Contractor | Road Passable - Caution Required | Fallen Tree |  | Crew attending
South | HELMSDALE RD | 7600 |  |  | 2022-07-25 | 12:47 | Roading Staff | Road Passable - Caution Required | Dropout - Underslip |  | signage required
South | HELMSDALE RD | 4500 |  |  | 2022-07-25 | 12:53 | Roading Staff | Road Passable - Caution Required | Flooding |  | signage required
South | COVE RD | 16333 |  |  | 2022-07-25 | 1:25 | Contractor | One Lane Only | Landslide - Overslip |  | Traffic management onsite, will be cleared today 25/7/22
North | NGUNGURU RD NTH |  | LHS | Just after passing lane | 2022-07-25 |  | Call Centre | One Lane Only | [5 empty] | 2022-07-25 | 14:00 | Cleared. However slip came down next to it afterwards and blocked. Re-entered on line 16
North | MARUA RD |  | LHS |  | 2022-07-25 |  | Call Centre | One Lane Only | [7 empty] | Pushed to side of road so both lanes are clear and signs installed. Still needs to be picked up
North | NGUNGURU RD NTH |  | Both |  | 2022-07-25 |  | Call Centre | One Lane Only | Fallen Tree |  | Tree Crew sent out | 2 hours |  | 2022-07-25 | 10am | Tree Cleared
North | HARRIS RD |  | LHS |  | 2022-07-25 |  | Call Centre | Road Open | Fallen Tree |  | Tree Crew sent out- Will be here after Ngunguru Rd complete | 2 hours |  | 2022-07-25 | 1130am | Tree Cleared
North | WHANGAREI HEADS RD NTH |  | Both |  | 2022-07-25 |  | Call Centre | Road Passable - Caution Required | Flooding |  | Signage inastalled |  |  | 2022-07-25 | 9am | Road opened - Debries still need to be removed from side of road.
North | WHANANAKI NORTH RD |  | LHS | Between Otonga Marua and Passed pigs head rd | 2022-07-25 |  | Call Centre | Road Closed | Flooding |  | Signage inastalled | Untill Flooding subsides
North | OCEAN BEACH RD |  | Both |  | 2022-07-25 |  | Call Centre | Road Open | Fallen Tree |  |  | 4 hours
North | NGUNGURU RD NTH |  | Both | Just after passing lane | 2022-07-25 | 2.30pm | Roading Staff | Road Closed | Landslide - Overslip |  | Closed for 5 hours then dowen to 1 lane for the night | 24 hours | Will push slip to side of the road to make safe tonight and clear tomorrow.
North | NGUNGURU RD NTH |  | RHS | Just passed the school | 2022-07-25 | 2pm | Call Centre | One Lane Only | Landslide - Overslip |  |  | 3 hours
North | RUSSELL RD (CTL) |  | Both | Punaruku - Between Whangaruru School and Whangaruru Wharf rd | 2022-07-25 |  | Roading Staff | Road Passable - Caution Required | Flooding |  | Signage inastalled | Untill Flooding subsides
North | KOKOPU RD |  | Both |  | 2022-07-25 |  | Roading Staff | Road Passable - Caution Required | Flooding |  | Signage inastalled | Untill Flooding subsides
North | WRIGHT RD |  | Both |  | 2022-07-25 |  | Roading Staff | Road Passable - Caution Required | Flooding |  | Signage inastalled | Untill Flooding subsides
North | MARUA RD |  | Both |  | 2022-07-25 |  | Call Centre | Road Passable - Caution Required | Flooding |  | Signage inastalled | Untill Flooding subsides
North | PIPIWAI RD NTH | 31500 | Both |  | 2022-07-25 |  | Roading Staff | Road Passable - Caution Required | Landslide - Overslip |  | Signage inastalled |  | Does cross white line but is not impacting traffic or blocking the lane
North |  |  | Both | Past school road under water | 2022-07-25 |  | Public | Road Closed | Flooding |  |  | Untill Flooding subsides
0
[18 empty] | 0 | 0 | CAUSEWAY ROAD ZONE T
CHAPEL STREET ZONE X
CHARLOTTE KEMP DRIVE ZONE S
CHERRINGTON ROAD ZONE T
CHURCH STREET (KAWAKAWA) ZONE T
CHURCH STREET (RUSSELL) ZONE X
CLARK ROAD (KERIKERI) ZONE S
CLASSEN ROAD ZONE K
CLENDON ESPLANADE ZONE K
CLIFFORD STREET ZONE M
COBHAM COURT ZONE S
COBHAM ROAD ZONE S
COCHRANE DRIVE ZONE R
COMMERCIAL STREET ZONE T
CONIFER LANE ZONE S
COOK ROAD ZONE M
COOKSON ROAD ZONE T
COTTLE HILL DRIVE ZONE S
COURTHOUSE LANE ZONE R
COUTTS AVENUE ZONE T
CROWN CRESCENT ZONE M
CUMBER ROAD ZONE M
CUMBER ROAD SIDE ROAD ZONE M
CURTIS ROAD ZONE K
DAROUX DRIVE ZONE R
DARWIN ROAD ZONE S
DAVIS CRESCENT (PAIHIA) ZONE T
DAVIS ROAD ZONE T
DAVIS STRONGMAN DRIVE ZONE S
DAVY ROAD ZONE T
DE HAVEN STREET ZONE T
DE MERLE STREET ZONE M
DE THIERRY STREET ZONE K
DEEMING ROAD ZONE X
DERRICK ROAD EXTENSION ZONE T
DERRICK ROAD ZONE T
DIAMOND ROAD ZONE J
DICKESON STREET ZONE M
DOELS ROAD (KAWAKAWA) ZONE T
DOMAIN ROAD ZONE T
DONALDSON ROAD ZONE M
DOONSIDE ROAD ZONE S
DOVES BAY ROAD ZONE S
DU FRESNE PLACE ZONE X
DU FRESNE PLACE EXTENSION ZONE X
DUDDY ROAD ZONE K
EDKINS ROAD (KERIKERI) ZONE S
EDMONDS ROAD ZONE S
ENGLISH BAY ROAD ZONE T
ENTERPRISE STREET ZONE M
EQUESTRIAN ZONE S
FACTORY ROAD ZONE T
FAIRLIE CRESCENT ZONE J
FAIRVIEW ROAD ZONE M
FAIRWAY DRIVE ZONE S
FALLS VIEW ROAD ZONE T
FLAGSTAFF HILL ZONE X
FLORENCE AVENUE ZONE X
FORDS ROAD ZONE W
FOREST ROAD ZONE M
FORREST HEIGHT ROAD ZONE S
FRANKLIN STREET ZONE T
FRASER ROAD ZONE T
FREESE PARK ROAD ZONE J
FULLER PLACE (KAIKOHE) ZONE M
FULLER TERRACE (KERIKERI) ZONE S
FURNESS ROAD ZONE S
GAMMONS ROAD ZONE P
GARDEN COURT ZONE T
GENERAL GATES AVENUE ZONE S
GERRARD ROAD ZONE P
GILBERT MAIR RISE ZONE X
GILES ROAD ZONE L
GILLIES ROAD (SH 1 KAWAKAWA) ZONE T
GILLIES STREET (EAST) ZONE T
GILLIES STREET (WEST) ZONE T
GILLS DRIVE (KAWAKAWA) ZONE T
GOFFE DRIVE ZONE T
GOFFE DRIVE RESERVE EXTENSION ZONE T
GOLF VIEW ROAD ZONE S
GOODWINS ROAD ZONE J
GOULD STREET ZONE X
GRAHAM ROAD ZONE N
GREEN LANE ZONE R
GREEN LANE EXTENSION ZONE R
GREENACRES DRIVE ZONE T
GREENWAY DRIVE ZONE S
GREY STREET (KAWAKAWA) ZONE T
GREYS LANE ZONE T
GROVE ROAD ZONE M
GUERIN STREET ZONE M
GUNDRY STREET ZONE K
GUTHRIE ROAD ZONE L
GUY ROAD (SH 12 KAIKOHE) ZONE M
HAILES ROAD ZONE W
HALL ROAD ZONE S
HALYARD LOOP ZONE T
HAMBLIN STREET ZONE K
HANNAH PLACE ZONE S
HANSEN ROAD (PURERUA) ZONE S
HANSEN ROAD (WAIMAMAKU) ZONE J
HAPANGA ROAD ZONE L
HAPPY VALLEY ROAD ZONE M
HARIRU ROAD ZONE R
HAROLD AVENUE ZONE M
HARRIS ROAD ZONE M
HARRISON ROAD ZONE M
HARRY'S PLACE ZONE T
HARURU FALLS ROAD ZONE T
HAUTAPU ROAD ZONE T
HAWKE DRIVE ZONE T
HAWKINS CRESCENT ZONE S
HAY ROAD ZONE T
HAZARD STREET ZONE X
HEKE STREET ZONE M
HENARE ROAD ZONE W
HERBERT ROAD (WAIARE) ZONE R
HERON HILL ZONE S
HEWITTS ROAD ZONE S
HIHITAHI RISE ZONE T
HIKUWAI ROAD ZONE X
HILLCREST ROAD (KAIKOHE) ZONE M
HIVES ROAD ZONE K
HOBSON ROAD (KERIKERI) ZONE S
HOBSON ROAD (OHAEWAI) ZONE M
HOMESTEAD ROAD ZONE S
HONE HEKE ROAD ZONE S
HONEY STREET ZONE K
HONGI STREET ZONE M
HOOKS AND HALLS ROAD ZONE J
HOPE AVENUE ZONE X
HORAHORA HEADS ROAD ZONE W
HOREKE ROAD ZONE L
HOSPITAL ROAD (KAWAKAWA) ZONE T
HULME DRIVE ZONE M
HUPARA ROAD ZONE T
HUPARA ROAD (EAST) ZONE T
IMMS ROAD (LAKE OMAPERE) ZONE M
INKSTERS ROAD ZONE W
IRONBARK ROAD ZONE R
JACARANDA PLACE ZONE S
JACKS BAY ROAD ZONE X
JACKSON ROAD ZONE K
JAMES CLENDON PLACE ZONE X
JAMES KEMP PLACE ZONE S
JAMES MCKENZIE WAY ZONE M
JAMES ROAD (MATAWAIA) ZONE W
JAMES STREET (RUSSELL) ZONE X
JAMIESON ROAD (RAWENE) ZONE K
JENKINS ROAD ZONE R
JENNINGS ROAD ZONE R
JOHNSON LANE ZONE T
JOHNSON ROAD (KAWAKAWA) ZONE T
JORDAN ROAD ZONE M
JOYCES ROAD ZONE T
KAHA PLACE ZONE X
KAHIKATEAROA ROAD ZONE S
KAHIKATOA ROAD ZONE M
KAIPATIKI ROAD ZONE T
KAKA ROAD ZONE W
KAKAPU ROAD ZONE X
KANE STREET (EAST) ZONE T
KANE STREET (WEST) ZONE T
KAPIRO ROAD ZONE S
KARAKA DRIVE ZONE S
KARAKA ROAD ZONE M
KARETU ROAD ZONE X
KARUHIRUHI ROAD ZONE K
KAURI PLACE ZONE M
KAWAKAWA-PAIHIA ROAD (SH 11 PAIHIA) ZONE T
KELLET STREET ZONE T
KELLY ROAD ZONE J
KEMP ROAD ZONE S
KEMPTHORNE ROAD ZONE X
KENDALL ROAD ZONE S
KENNEDY STREET ZONE T
KENT STREET (RUSSELL) ZONE X
KEOGH ROAD ZONE T
KERI DOWNS ROAD ZONE S
KERIKERI GROVE ZONE S
KERIKERI INLET ROAD ZONE S
KERIKERI ROAD ZONE S
KILOUNTAIN PLACE ZONE S
KING STREET ZONE S
KINGFISHER DRIVE ZONE S
KINGFISHER ROAD ZONE X
KINGI ROAD ZONE T
KINGS ROAD ZONE T
KINGSTON PLACE ZONE S
KLINAC LANE ZONE S
KNUDSENS ROAD ZONE P
KOHEWHATA ROAD ZONE M
KOKINGA POINT ROAD ZONE X
KOKOHUIA ROAD ZONE J
KORANAE ROAD ZONE R
KOROPEWA ROAD ZONE R
KOTARE HEIGHTS ZONE S
KOTUKU ROAD ZONE S
KOUTU BEACH ROAD ZONE K
KOUTU LOOP ROAD ZONE K
KOUTU POINT ROAD ZONE K
KOWHAI AVENUE (KAIKOHE) ZONE M
KOWHAI CRESCENT (PAIHIA) ZONE T
KUPA ROAD ZONE W
KURA ROAD ZONE T
KURIPARI ROAD ZONE S
LAKE ROAD (OKAIHAU) ZONE M
LAMBERG ROAD ZONE M
LANARK ROAD ZONE S
LANDING ROAD (KERIKERI) ZONE S
LANES ROAD ZONE X
LAWN STREET ZONE M
LEAITY STREET ZONE T
LEMON GROVE ZONE R
LEONARD STREET ZONE T
LEWIS ROAD ZONE M
LICHEN GROVE ZONE X
LILLY POND LANE ZONE T
LINDVART STREET ZONE M
LITTLE QUEEN STREET ZONE X
LODORE ROAD ZONE S
LODORE ROAD (EAST) ZONE S
LONG BEACH ROAD ZONE X
LONGS ROAD ZONE W
LOVATT ROAD ZONE W
LUCAS ROAD ZONE T
LUDBROOKS ROAD ZONE T
LUDBROOKS ROAD (LOOP) ZONE T
LYON STREET ZONE T
MACDONNELL ROAD ZONE L
MACMURRAY ROAD ZONE T
MAHINA ROAD ZONE K
MAJOR BRIDGE DRIVE ZONE X
MAKO LANE (PAIHIA) ZONE T
MANAWAORA ROAD ZONE X
MANDENO DRIVE ZONE S
MANGAKAHIA ROAD ZONE M
MANGAKARETU ROAD ZONE S
MANGAPARA ROAD (WHIRINAKI) ZONE K
MANGAPUPU ROAD ZONE K
MANGATARAIRE ROAD ZONE L
MANGATAWA ROAD ZONE N
MANGATOA ROAD ZONE N
MANGU ROAD ZONE W
MANNING STREET ZONE K
MANUWAI LANE ZONE R
MARAENUI DRIVE ZONE S
MARINA RISE ZONE T
MARINER STREET ZONE K
MARINO PLACE ZONE M
MARLOW ROAD ZONE W
MARMON STREET (EAST) ZONE K
MARMON STREET (WEST) ZONE K
MAROMAKU SCHOOL ROAD ZONE W
MAROMAKU-TOWAI ROAD ZONE W
MARSDEN PLACE (KERIKERI) ZONE S
MARSDEN ROAD (PAIHIA) ZONE T
MARSHALL ROAD ZONE T
MARSHALL STREET (MOEREWA) ZONE T
MARTIN ROAD ZONE J
MARTIN ROAD (POKERE) ZONE W
MASON AVENUE (MOEREWA) ZONE T
MASONIC LANE ZONE S
MASONS ROAD ZONE W
MASSEY STREET ZONE T
MATAUWHI ROAD ZONE X
MATAWAIA-MAROMAKU ROAD ZONE W
MATENE ROAD ZONE P
MAWSON AVENUE ZONE R
MCCAUGHAN ROAD ZONE R
MCDONALDS ROAD (OROMAHOE) ZONE T
MCDONELL STREET ZONE K
MCFARLANE STREET (NORTH) ZONE T
MCFARLANE STREET (SOUTH) ZONE T
MCINTYRES ROAD ZONE T
MCKENZIE ROAD (PURERUA) ZONE S
MCLEOD ROAD ZONE S
MEMORIAL AVENUE ZONE M
MICHIE STREET ZONE M
MIHI ROAD ZONE M
MIHIRATA ROAD ZONE W
MILL LANE ZONE S
MILL ROAD ZONE T
MIRO AVENUE ZONE J
MISSION OAK ROAD ZONE L
MISSION ROAD (KERIKERI) ZONE S
MITCHELL ROAD ZONE J
MOANA AVENUE ZONE T
MOEHAU ROAD ZONE L
MONTROSE ROAD ZONE S
MONUMENT ROAD ZONE W
MONUMENT ROAD (KAIKOHE) ZONE M
MOORING CLOSE ZONE S
MORGANS ROAD ZONE W
MOTUKIORE ROAD ZONE L
MOTUTOA ROAD ZONE K
MOUNTAIN ROAD ZONE K
MUDGWAY ROAD ZONE M
NAUTICAL DRIVE ZONE T
NELSONS ROAD ZONE W
NESS ROAD ZONE R
NEUMAN STREET (SH 11 KAWAKAWA) ZONE T
NEWTON ROAD ZONE J
NEWTON WATTS DRIVE ZONE S
NGAHUHU ROAD ZONE T
NGAPIPITO ROAD ZONE M
NGAPUA PLACE ZONE M
NGAPUHI ROAD ZONE R
NGAPUHI ROAD (KAIKOHE) ZONE M
NGAWHA SCHOOL ROAD ZONE M
NGAWHA SPRINGS ROAD ZONE M
NGAWHITU ROAD ZONE T
NIMMO STREET (CENTRAL) ZONE K
NIMMO STREET (EAST) ZONE K
NIMMO STREET (WEST) ZONE K
NINIHI ROAD ZONE N
NISBET STREET ZONE T
NORFOLK PLACE ZONE S
NORTH ROAD (SH 11 KAWAKAWA) ZONE T
NOVA STREET ZONE M
NOY ROAD ZONE T
OAKRIDGE DRIVE ZONE S
OETZMAN ROAD ZONE W
OHARA STREET ZONE M
OHURI ROAD ZONE K
OIHI ROAD ZONE S
OKAIHAU ROAD ZONE M
OKAKA ROAD ZONE L
OKIATO ROAD ZONE X
OKOKAKO ROAD ZONE S
OKORO ROAD ZONE M
OKURA DRIVE ZONE S
OLD BAY ROAD ZONE M
OLD NORTH ROAD ZONE T
OLD NORTH ROAD EXTENSION ZONE T
OLD VALLEY ROAD ZONE M
OLD WHANGAE ROAD ZONE T
OMANAIA ROAD ZONE K
OMANAIA SCHOOL ROAD ZONE K
OMAPERE ROAD ZONE M
ONEKURA ROAD ZONE R
ONEROA ROAD ZONE X
OPAHI STATION ROAD ZONE W
OPARA ROAD ZONE K
OPITO BAY ROAD ZONE S
ORAKAU ROAD ZONE P
ORANGEWOOD LANE ZONE R
ORCHARD ROAD (HARURU FALLS) ZONE T
ORCHARD ROAD (KAPIRO) ZONE S
ORIPIRO ROAD ZONE S
ORIRA ROAD ZONE M
ORMONDE PLACE ZONE M
OROMAHOE ROAD ZONE T
OROMAHOE SCHOOL ROAD ZONE T
ORRS ROAD ZONE M
OSBOURNE ROAD ZONE T
OTAENGA ROAD ZONE P
OTAERE ROAD ZONE M
OTAHA ROAD ZONE S
OTAHI ROAD ZONE K
OTAMARUA ROAD ZONE X
OTATARA MARAE ROAD ZONE L
OTAUA ROAD ZONE N
OTIRIA ROAD ZONE T
OWAE ROAD ZONE T
PA ROAD ZONE S
PACKERS ROAD ZONE T
PAIAKA ROAD ZONE W
PAKANAE CEMETERY ROAD ZONE J
PAKARU ROAD ZONE T
PAKEHAUA ROAD ZONE X
PALM DRIVE ZONE S
PANIORA ROAD ZONE J
PANORAMA ROAD ZONE T
PARAHA ROAD ZONE W
PAREMATA ROAD ZONE M
PARETU DRIVE ZONE S
PARK ROAD ZONE M
PARKERS ROAD ZONE N
PARNELL STREET ZONE K
PAROA ROAD ZONE X
PARROT ROAD ZONE N
PEACOCK GARDEN DRIVE ZONE S
PEACOCK GARDEN DRIVE EXTENSION ZONE S
PEMBROKE STREET ZONE T
PENNEY CRESCENT (KAIKOHE) ZONE M
PENNEY STREET (OPUA) ZONE T
PERAS ROAD ZONE L
PERI ROAD ZONE W
PERRY ROAD ZONE M
PICADILLY ROAD ZONE P
PICKMERE LANE ZONE S
PINE HILL ROAD ZONE J
PINEHILL ROAD ZONE T
PIONEERS WALK ZONE J
PIPIROA ROAD ZONE X
PIPIWAI ROAD ZONE W
PITT STREET ZONE X
PLUNKET STREET ZONE T
POIETE ROAD ZONE M
POINT VERONICA DRIVE ZONE T
POINT VERONICA DRIVE EXTENSION ZONE T
POKAPU ROAD ZONE T
POKAS ROAD ZONE J
POKERE ROAD ZONE W
POMARE ROAD ZONE X
POPLAR LANE ZONE S
POROTU ROAD ZONE T
POUNAMU PLACE ZONE S
PROSPECT STREET ZONE X
PUHA ROAD ZONE L
PUHITIA ROAD ZONE W
PUIA ROAD ZONE M
PUKAWA ROAD (WHIRINAKI) ZONE K
PUKEPOTO ROAD (OKAIHAU) ZONE M
PUKETI ROAD ZONE M
PUKETIRO PLACE ZONE T
PUKETONA ROAD ZONE T
PUKETOTARA ROAD ZONE S
PUKETUTU DRIVE ZONE T
PUKEWHAO ROAD ZONE L
PUKEWHAU ROAD ZONE S
PUNAKITERE LOOP ROAD ZONE N
PUNGAERE ROAD ZONE R
PURDY STREET ZONE M
PURERUA ROAD ZONE R
QUARRY ROAD (KAIKOHE) ZONE M
QUEEN STREET (KAWAKAWA) (SH 1) ZONE T
QUEEN STREET (RUSSELL) ZONE X
QUEENS VIEW ROAD ZONE X
QUINCES LANDING ZONE S
RAHIRI SETTLEMENT ROAD ZONE M
RAIHARA STREET ZONE M
RAINBOW FALLS ROAD ZONE S
RAKAUTAO ROAD ZONE M
RAKAUWAHIA ROAD ZONE M
RAMSEY ROAD ZONE L
RANFURLY STREET ZONE T
RANGE ROAD ZONE T
RANGIAHUA ROAD ZONE M
RANGIHAMAMA ROAD ZONE M
RANGIHOUA ROAD ZONE S
RANGITANE LOOP ROAD ZONE S
RANGITANE LOOP ROAD EXTENSION ZONE S
RANGITANE ROAD ZONE S
RANKIN STREET ZONE M
RANUI AVENUE ZONE S
RANUI ROAD ZONE T
RAPARAPA ROAD ZONE P
RARERE TERRACE ZONE S
RATA TIPENE ROAD ZONE W
RAWENE ROAD ZONE K
RAWHITI ROAD (NORTH) ZONE X
RAWHITI ROAD (SOUTH) ZONE X
RAYMOND STREET ZONE T
RAYNER STREET ZONE T
RECREATION ROAD ZONE M
REDCLIFFS ROAD ZONE S
REED STREET (MOEREWA) ZONE T
REINGA ROAD ZONE S
REMUERA SETTLEMENT ROAD ZONE M
RENWICK ROAD ZONE N
RESERVOIR ROAD ZONE M
RETREAT ROAD ZONE T
REWA PLACE ZONE X
RICHARDSON STREET ZONE T
RICHARDSON STREET (WEST) ZONE T
RIDDELL ROAD ZONE S
RIGDEN ROAD ZONE T
RIMU PLACE ZONE M
RIPI STREET ZONE M
RIVER DRIVE ROAD ZONE S
RIVERSTREAM DRIVE ZONE R
RIVERVIEW ROAD ZONE S
ROBERTSON STREET ZONE X
RODGER ROAD ZONE T
ROGER ROAD ZONE N
ROSELLA DRIVE ZONE T
ROSS STREET ZONE T
ROUTLEY AVENUE ZONE M
ROWSELL HEIGHTS ZONE M
ROWSELL LANE ZONE S
RUAPEKAPEKA ROAD ZONE T
RUSK ROAD ZONE W
RUSSEK ROAD ZONE W
RUSSELL ESPLANADE ZONE K
RUSSELL HEIGHTS ZONE X
RUSSELL-WHAKAPARA ROAD ZONE X
SAIES ROAD ZONE T
SAMMAREE PLACE ZONE S
SANDYS ROAD ZONE S
SAWARD ROAD ZONE M
SCHOOL ROAD (PAIHIA) ZONE T
SCORESBY STREET ZONE T
SCOTTS ROAD ZONE M
SEAVIEW HEIGHTS ROAD ZONE T
SEAVIEW ROAD (PAIHIA) ZONE T
SELWYN PLACE (KERIKERI) ZONE S
SELWYN ROAD (PAIHIA) ZONE T
SERVICE LANE #1 (KAIKOHE) ZONE M
SERVICE LANE #2 (KAIKOHE) ZONE M
SETTLEMENT ROAD ZONE T
SETTLERS WAY ZONE M
SHAW STREET ZONE M
SHEPHERDS ROAD (KERIKERI) ZONE S
SHEPHERDS ROAD (SOUTH) ZONE S
SHIRLEY ROAD ZONE R
SHOWGROUND ROAD ZONE R
SIGNAL STATION ROAD ZONE J
SIGNALS ROAD ZONE M
SILKWOOD LANE ZONE S
SIR GEORGE BACK STREET ZONE T
SIR JAMES HENARE PLACE ZONE T
SIR WILLIAM HALE CRESCENT ZONE T
SKUDDERS BEACH ROAD ZONE S
SMEATH ROAD (HUPARA) ZONE T
SMEATH ROAD (KAWAKAWA) ZONE T
SMITH CAMP ROAD ZONE T
SMITH GRAY ROAD ZONE X
SMITH ROAD (MOEREWA) ZONE T
SMOOTHY ROAD ZONE J
SNOWDON AVENUE ZONE T
SOMERVILLE ROAD ZONE R
SOUTHVIEW PLACE ZONE M
SPINNAKER POINT ZONE S
SQUIRES LANE ZONE M
ST ANDREWS PLACE ZONE S
STANNERS ROAD ZONE S
STATE HIGHWAY 1 (KAWAKAWA) ZONE T
STATE HIGHWAY 1 (MOEREWA) ZONE T
STATE HIGHWAY 1 (OHAEAWAI) ZONE M
STATE HIGHWAY 1 (OKAIHAU) ZONE M
STATE HIGHWAY 12 (OHAEAWAI) ZONE M
STATE HIGHWAY 12 (OPONONI) ZONE J
STATE HIGHWAY 12 (WAIMAMUKU) ZONE J
STATION ROAD (KAIKOHE) ZONE M
STATION ROAD (KAWAKAWA) ZONE T
STATION ROAD (MOEREWA) ZONE T
STELLA DRIVE (EAST) ZONE S
STELLA DRIVE (WEST) ZONE S
STEWARDS ROAD ZONE N
STURGE ROAD ZONE M
SULLIVAN ROAD EXTENSION ZONE T
SULLIVANS ROAD ZONE T
SYDNEY STREET ZONE M
TAHEKE ROAD ZONE L
TAHEKE ROAD (SH 12 KAIKOHE) ZONE M
TAHIWI ROAD ZONE W
TAHUNA ROAD (PAIHIA) ZONE T
TAIKIRAU ROAD ZONE W
TAITA ROAD ZONE J
TAKOU BAY ROAD ZONE S
TANA ROAD ZONE T
TANIKAHA LANE ZONE R
TAPEKA ROAD ZONE X
TAPUHI ROAD ZONE W
TARAIRE STREET (KAIKOHE) ZONE M
TARAKIHI ROAD ZONE T
TARUTARU LANE ZONE S
TASMAN PLACE ZONE S
TAU HENARE DRIVE ZONE T
TAUMATA CLOSE ZONE T
TAUMATAMAKUKU CRESCENT ZONE T
TAUMATAMAKUKU ROAD ZONE T
TAUMATAWIWI STREET ZONE J
TAWA STREET ZONE M
TAWANUI ROAD ZONE M
TAWATA ROAD ZONE N
TE AHU AHU ROAD ZONE R
TE HAUMI DRIVE ZONE T
TE HUNOKE ROAD ZONE J
TE IRENGA ROAD ZONE P
TE IRENGA WEST ROAD ZONE P
TE KAHU STREET ZONE T
TE KARUWHA PARADE ZONE T
TE KEMARA AVENUE ZONE T
TE KOWHAI POINT ROAD ZONE S
TE MAORI ROAD ZONE R
TE OHU ROAD ZONE K
TE ORO ROAD ZONE T
TE PUA ROAD (KAIKOHE) ZONE M
TE RA PLACE ZONE M
TE RA ROAD ZONE S
TE RA ROAD EXTENSION ZONE S
TE RANGI CROSS ZONE T
TE TII ROAD ZONE S
TE TII ROAD EXTENSION ZONE S
TE TIO ROAD ZONE M
TE WAHAPU ROAD ZONE X
TE WAIAROHIA ROAD ZONE J
TENNYSON STREET (EAST) ZONE M
TENNYSON STREET (WEST) ZONE M
THE ANCHORAGE ZONE S
THE ANCHORAGE EAST ZONE S
THE LOOKOUT ZONE S
THE STRAND (NORTH) ZONE X
THE STRAND (SOUTH) ZONE X
THORPE ROAD ZONE M
TIKORANGI ROAD ZONE S
TIPENE ROAD ZONE W
TIRAIRAKA TERRACE ZONE X
TIROHANGA ROAD ZONE T
TITORE WAY ZONE X
TOHITAPU ROAD ZONE T
TOI TRACK ZONE X
TOIA ROAD ZONE M
TOKAWHERO ROAD ZONE P
TOOTS DRIVE ZONE T
TOPPS ROAD ZONE R
TOTARA PLACE (KAIKOHE) ZONE M
TOTARA PLACE (KERIKERI) ZONE S
TUHUNA ROAD (KAIKOHE) ZONE M
TUI GROVE (PAIHIA) ZONE T
TUI PLACE (KERIKERI) ZONE S
TUI STREET (EAST) ZONE M
TUI STREET (OKAIHAU) ZONE M
TUI STREET (WEST) ZONE M
TUTAHI PLACE ZONE S
TYREE ROAD ZONE S
UMAWERA SCHOOL ROAD ZONE M
UPOKORAU ROAD ZONE R
URUTAWA DRIVE ZONE S
URUTI ROAD ZONE X
VALENCIA LANE ZONE S
VERONICA STREET ZONE T
VIEW ROAD ZONE J
VOGEL STREET ZONE T
VUJCICH ROAD ZONE K
WAHAMITI CEMETERY ROAD ZONE T
WAIANGA PLACE ZONE J
WAIARE ROAD ZONE R
WAIARUHE WAY ZONE X
WAIHOTA ROAD ZONE J
WAIHUKA ROAD ZONE J
WAIKARAMU ROAD ZONE M
WAIKARE ROAD ZONE T
WAIKARE VALLEY ROAD ZONE X
WAIKERIKERI ROAD ZONE L
WAIKERIKERI ROAD EXTENSION ZONE L
WAIKINO ROAD ZONE T
WAIKUKU ROAD ZONE R
WAIMA SCHOOL ROAD ZONE L
WAIMA VALLEY ROAD ZONE L
WAIMAMAKU BEACH ROAD ZONE J
WAIMANGARO ROAD ZONE T
WAIMATE NORTH ROAD ZONE S
WAIMATENUI / MATARAUA ROAD ZONE M
WAIOHANGA ROAD ZONE M
WAIOMIO ROAD (KAWAKAWA) ZONE T
WAIOMIO ROAD (WAIOMIO) ZONE T
WAIONE ROAD ZONE K
WAIOTEMARAMA GORGE ROAD ZONE J
WAIOTU ROAD ZONE W
WAIPAPA INDUSTRIAL ZONE R
WAIPAPA LANDING PLACE ZONE S
WAIPAPA LOOP ROAD ZONE R
WAIPAPA ROAD ZONE R
WAIPAPA WEST ROAD ZONE R
WAIPUNA PLACE ZONE T
WAITAHEKE ROAD ZONE M
WAITOTARA DRIVE ZONE S
WAKELIN ROAD ZONE S
WALLIS ROAD ZONE M
WAOKU ROAD ZONE L
WARD DRIVE ZONE T
WARD DRIVE (EAST) ZONE T
WATERS LANE ZONE S
WATERVIEW ZONE T
WEBSTER STREET ZONE K
WEHIRUA ROAD ZONE M
WEKAWEKA ROAD ZONE J
WELLINGTON STREET ZONE X
WELLSFORD ROAD ZONE K
WENDYWOOD LANE ZONE S
WENTWORTH TERRACE ZONE S
WHAAKAURU VALLEY ROAD ZONE X
WHAKATAHA ROAD ZONE R
WHANGAE ROAD ZONE R
WHANGARURU NORTH ROAD ZONE X
WHARAU ROAD ZONE S
WHAREKAWA ROAD ZONE K
WHARENGAERE ROAD ZONE S
WHAREPUNGA ROAD ZONE N
WHARF ROAD (HARURU FALLS) ZONE T
WHARF ROAD (OPONONI) ZONE J
WHIRINAKI SCHOOL ROAD ZONE K
WHITE ROAD (RANGIAHUA) ZONE M
WHITEMANS ROAD ZONE T
WHIU ROAD ZONE N
WIHONGI STREET ZONE M
WIKAIRAS ROAD ZONE K
WILLIAMS AVENUE (KAIKOHE) ZONE M
WILLIAMS ROAD ZONE T
WILLIAMS STREET (KAWAKAWA) ZONE T
WILLIAMS STREET (MOEREWA) ZONE T
WILLOW PARK PLACE ZONE M
WILLOWBROOK STREET ZONE T
WILSON ROAD ZONE T
WINDSOR ROAD ZONE M
WIROA ROAD ZONE S
WITANA ROAD ZONE M
WOOD STREET ZONE M
WOODBINE ROAD (KAIKOHE) ZONE M
WOODLEY DRIVE ZONE S
WOODLEY PLACE ZONE T
WRIGHTSONS ROAD ZONE R
WYNYARD STREET (KAWAKAWA) ZONE T
WYNYARD STREET (MOEREWA) ZONE T
YACHT DRIVE (OPITO BAY) ZONE S
YORK STREET ZONE X
YORKE ROAD ZONE T
YORKE ROAD (EAST) ZONE T
YOUNGS ROAD ZONE N

## Kaipara
Situation Report | [6 empty] | Name of Event: | Severe Weather Warning - 24/25 July 22
Local Authority Area: |  |  |  | Kaipara District Council
SitRep No. |  | 3 |  | (ref Page 235 Section SI02 - Incident Response)
Date: | 2022-07-25
Time: | 4PM |  |  | ( Daily SitReps due before 8am, 12noon and 4pm - or as agreed with the NTA Engineer's Rep)
Contract Area | Road Name | Route Position | Side | Site location description (eg. Xkm past Y road) | Date reported | Time | Source of Info (Contractor, call centre, public etc) | ROAD STATUS (see column 'w' notes) | Road Damage (see column 'v' notes) | RAMM Dispatch ID | Action Taken | Estimated Outage | Any planned action required | Date Resolved | Time Resolved | Additional Notes and Comments | Initial Response Cost | Claimed to date | Permanent repair cost
North | MANGATU RD (238) | 3000 | Centre | 3000m from beginning of road | 2022-07-25 | 8:04 | Contractor | Road Open | Fallen Tree | 227823 | Inspected | N/A | Tree removed by sub-contractor |  |  | Tree cleared and road fully open
North | AVOCA EAST RD (206) | 6087 | Centre | As per RP | 2022-07-25 | 9:53 | Public | Road Open | Fallen Tree | 227828 | Inspected | N/A | Tree branch removed by Ventia crew |  |  | Tree cleared and road fully open
South | TE WHAI ST (709) | 158 | Centre | End of the cul-de-sac | 250734 | 9:27 | Public | Road Passable - Caution Required | Flooding |  | Inspected | N/A | Created channel to divert water |  |  | Water subsiding, sandbags enroute to divert water away from houses
North | CHARITY HILL RD (117) | 878 Approx | LHS | RP is Approx | 2022-07-25 | 10:45 | Public | Road Passable - Caution Required | Fallen Tree |  | Inspected | 1hr | Ventia crew onsite to remove tree |  |  | Tree overhanging the road about to fall
North | MARLBOROUGH RD (241) | 6405 | LHS | As per RP | 2022-07-25 | 10:20 | Contractor | Road Open | Fallen Tree |  | Inspected | N/A | Tree removed by Ventia crew |  |  | Road open
North | MORGAN RD (248) | 200 | RHS | As per RP | 2022-07-25 | 10:20 | Contractor | Road Open | Fallen Tree |  | Inspected | N/A | Tree removed by Ventia Crew |  |  | Road open
North | OTARA POINT RD (159) | 1458 | Both | As per RP | 2022-07-25 | 10:52 | Contractor | Road Open | Surface water hazard |  | Inspected | N/A | Inlet has been cleared and water is subsiding |  |  | Road open
South | PAPAROA STATION RD (402) | 6840 | RHS | As per RP | 2022-07-25 | 11:30 | Contractor | Road Open | Fallen Tree | 227830 | Inspected | N/A | Tree removed by Ventia Crew |  |  | Tree cleared and road fully open
North | PINAKI RD (162) | 875 | RHS | As per RP | 2022-07-25 | 11:46 | Contractor | Road Open | Surface water hazard |  | Inspected | N/A | Inlet has been cleared and water is subsiding |  |  | Road open
North | MITITAI RD (145) | 19630 | Centre | As per RP | 2022-07-25 | 8:56 | Contractor | Road Open | Fallen Tree | 227824 | Inspected | N/A | Tree removed by sub-contractor |  |  | Tree cleared and road fully open
North | MAROPIU RD (242) | 3686 | RHS | As per RP | 2022-07-25 | 12:57 | Contractor | Road Open | Fallen Tree |  | Inspected | N/A | Tree has been cleared by sub-contractor |  |  | Tree cleared and road fully open
North | FRITH RD (219) | 528 | LHS | As per RP | 2022-07-25 | 13:28 | Contractor | Road Passable - Caution Required | Fallen Tree |  | Inspected | 2hrs | Team veg onsite to clear tree
North | AVOCA EAST RD (206) | 1456 |  | As per RP | 2022-07-25 |  | Contractor | Road Passable - Caution Required | Fallen Tree | 227867 | Inspected | N/A | T8 Trees to clear remaining debris tomorrow, road is open |  |  | Tree mostly removed by unknown persons
North | AVOCA EAST RD (206) | 970 |  | As per RP | 2022-07-25 |  | Contractor | Road Passable - Caution Required | Fallen Tree | 227868 | Inspected | N/A | T8 trees to remove tree tomorrow |  |  | Tree overhanging the road
CAUSEWAY ROAD ZONE T
CHAPEL STREET ZONE X
CHARLOTTE KEMP DRIVE ZONE S
CHERRINGTON ROAD ZONE T
CHURCH STREET (KAWAKAWA) ZONE T
CHURCH STREET (RUSSELL) ZONE X
CLARK ROAD (KERIKERI) ZONE S
CLASSEN ROAD ZONE K
CLENDON ESPLANADE ZONE K
CLIFFORD STREET ZONE M
COBHAM COURT ZONE S
COBHAM ROAD ZONE S
COCHRANE DRIVE ZONE R
COMMERCIAL STREET ZONE T
CONIFER LANE ZONE S
COOK ROAD ZONE M
COOKSON ROAD ZONE T
COTTLE HILL DRIVE ZONE S
COURTHOUSE LANE ZONE R
COUTTS AVENUE ZONE T
CROWN CRESCENT ZONE M
CUMBER ROAD ZONE M
CUMBER ROAD SIDE ROAD ZONE M
CURTIS ROAD ZONE K
DAROUX DRIVE ZONE R
DARWIN ROAD ZONE S
DAVIS CRESCENT (PAIHIA) ZONE T
DAVIS ROAD ZONE T
DAVIS STRONGMAN DRIVE ZONE S
DAVY ROAD ZONE T
DE HAVEN STREET ZONE T
DE MERLE STREET ZONE M
DE THIERRY STREET ZONE K
DEEMING ROAD ZONE X
DERRICK ROAD EXTENSION ZONE T
DERRICK ROAD ZONE T
DIAMOND ROAD ZONE J
DICKESON STREET ZONE M
DOELS ROAD (KAWAKAWA) ZONE T
DOMAIN ROAD ZONE T
DONALDSON ROAD ZONE M
DOONSIDE ROAD ZONE S
DOVES BAY ROAD ZONE S
DU FRESNE PLACE ZONE X
DU FRESNE PLACE EXTENSION ZONE X
DUDDY ROAD ZONE K
EDKINS ROAD (KERIKERI) ZONE S
EDMONDS ROAD ZONE S
ENGLISH BAY ROAD ZONE T
ENTERPRISE STREET ZONE M
EQUESTRIAN ZONE S
FACTORY ROAD ZONE T
FAIRLIE CRESCENT ZONE J
FAIRVIEW ROAD ZONE M
FAIRWAY DRIVE ZONE S
FALLS VIEW ROAD ZONE T
FLAGSTAFF HILL ZONE X
FLORENCE AVENUE ZONE X
FORDS ROAD ZONE W
FOREST ROAD ZONE M
FORREST HEIGHT ROAD ZONE S
FRANKLIN STREET ZONE T
FRASER ROAD ZONE T
FREESE PARK ROAD ZONE J
FULLER PLACE (KAIKOHE) ZONE M
FULLER TERRACE (KERIKERI) ZONE S
FURNESS ROAD ZONE S
GAMMONS ROAD ZONE P
GARDEN COURT ZONE T
GENERAL GATES AVENUE ZONE S
GERRARD ROAD ZONE P
GILBERT MAIR RISE ZONE X
GILES ROAD ZONE L
GILLIES ROAD (SH 1 KAWAKAWA) ZONE T
GILLIES STREET (EAST) ZONE T
GILLIES STREET (WEST) ZONE T
GILLS DRIVE (KAWAKAWA) ZONE T
GOFFE DRIVE ZONE T
GOFFE DRIVE RESERVE EXTENSION ZONE T
GOLF VIEW ROAD ZONE S
GOODWINS ROAD ZONE J
GOULD STREET ZONE X
GRAHAM ROAD ZONE N
GREEN LANE ZONE R
GREEN LANE EXTENSION ZONE R
GREENACRES DRIVE ZONE T
GREENWAY DRIVE ZONE S
GREY STREET (KAWAKAWA) ZONE T
GREYS LANE ZONE T
GROVE ROAD ZONE M
GUERIN STREET ZONE M
GUNDRY STREET ZONE K
GUTHRIE ROAD ZONE L
GUY ROAD (SH 12 KAIKOHE) ZONE M
HAILES ROAD ZONE W
HALL ROAD ZONE S
HALYARD LOOP ZONE T
HAMBLIN STREET ZONE K
HANNAH PLACE ZONE S
HANSEN ROAD (PURERUA) ZONE S
HANSEN ROAD (WAIMAMAKU) ZONE J
HAPANGA ROAD ZONE L
HAPPY VALLEY ROAD ZONE M
HARIRU ROAD ZONE R
HAROLD AVENUE ZONE M
HARRIS ROAD ZONE M
HARRISON ROAD ZONE M
HARRY'S PLACE ZONE T
HARURU FALLS ROAD ZONE T
HAUTAPU ROAD ZONE T
HAWKE DRIVE ZONE T
HAWKINS CRESCENT ZONE S
HAY ROAD ZONE T
HAZARD STREET ZONE X
HEKE STREET ZONE M
HENARE ROAD ZONE W
HERBERT ROAD (WAIARE) ZONE R
HERON HILL ZONE S
HEWITTS ROAD ZONE S
HIHITAHI RISE ZONE T
HIKUWAI ROAD ZONE X
HILLCREST ROAD (KAIKOHE) ZONE M
HIVES ROAD ZONE K
HOBSON ROAD (KERIKERI) ZONE S
HOBSON ROAD (OHAEWAI) ZONE M
HOMESTEAD ROAD ZONE S
HONE HEKE ROAD ZONE S
HONEY STREET ZONE K
HONGI STREET ZONE M
HOOKS AND HALLS ROAD ZONE J
HOPE AVENUE ZONE X
HORAHORA HEADS ROAD ZONE W
HOREKE ROAD ZONE L
HOSPITAL ROAD (KAWAKAWA) ZONE T
HULME DRIVE ZONE M
HUPARA ROAD ZONE T
HUPARA ROAD (EAST) ZONE T
IMMS ROAD (LAKE OMAPERE) ZONE M
INKSTERS ROAD ZONE W
IRONBARK ROAD ZONE R
JACARANDA PLACE ZONE S
JACKS BAY ROAD ZONE X
JACKSON ROAD ZONE K
JAMES CLENDON PLACE ZONE X
JAMES KEMP PLACE ZONE S
JAMES MCKENZIE WAY ZONE M
JAMES ROAD (MATAWAIA) ZONE W
JAMES STREET (RUSSELL) ZONE X
JAMIESON ROAD (RAWENE) ZONE K
JENKINS ROAD ZONE R
JENNINGS ROAD ZONE R
JOHNSON LANE ZONE T
JOHNSON ROAD (KAWAKAWA) ZONE T
JORDAN ROAD ZONE M
JOYCES ROAD ZONE T
KAHA PLACE ZONE X
KAHIKATEAROA ROAD ZONE S
KAHIKATOA ROAD ZONE M
KAIPATIKI ROAD ZONE T
KAKA ROAD ZONE W
KAKAPU ROAD ZONE X
KANE STREET (EAST) ZONE T
KANE STREET (WEST) ZONE T
KAPIRO ROAD ZONE S
KARAKA DRIVE ZONE S
KARAKA ROAD ZONE M
KARETU ROAD ZONE X
KARUHIRUHI ROAD ZONE K
KAURI PLACE ZONE M
KAWAKAWA-PAIHIA ROAD (SH 11 PAIHIA) ZONE T
KELLET STREET ZONE T
KELLY ROAD ZONE J
KEMP ROAD ZONE S
KEMPTHORNE ROAD ZONE X
KENDALL ROAD ZONE S
KENNEDY STREET ZONE T
KENT STREET (RUSSELL) ZONE X
KEOGH ROAD ZONE T
KERI DOWNS ROAD ZONE S
KERIKERI GROVE ZONE S
KERIKERI INLET ROAD ZONE S
KERIKERI ROAD ZONE S
KILOUNTAIN PLACE ZONE S
KING STREET ZONE S
KINGFISHER DRIVE ZONE S
KINGFISHER ROAD ZONE X
KINGI ROAD ZONE T
KINGS ROAD ZONE T
KINGSTON PLACE ZONE S
KLINAC LANE ZONE S
KNUDSENS ROAD ZONE P
KOHEWHATA ROAD ZONE M
KOKINGA POINT ROAD ZONE X
KOKOHUIA ROAD ZONE J
KORANAE ROAD ZONE R
KOROPEWA ROAD ZONE R
KOTARE HEIGHTS ZONE S
KOTUKU ROAD ZONE S
KOUTU BEACH ROAD ZONE K
KOUTU LOOP ROAD ZONE K
KOUTU POINT ROAD ZONE K
KOWHAI AVENUE (KAIKOHE) ZONE M
KOWHAI CRESCENT (PAIHIA) ZONE T
KUPA ROAD ZONE W
KURA ROAD ZONE T
KURIPARI ROAD ZONE S
LAKE ROAD (OKAIHAU) ZONE M
LAMBERG ROAD ZONE M
LANARK ROAD ZONE S
LANDING ROAD (KERIKERI) ZONE S
LANES ROAD ZONE X
LAWN STREET ZONE M
LEAITY STREET ZONE T
LEMON GROVE ZONE R
LEONARD STREET ZONE T
LEWIS ROAD ZONE M
LICHEN GROVE ZONE X
LILLY POND LANE ZONE T
LINDVART STREET ZONE M
LITTLE QUEEN STREET ZONE X
LODORE ROAD ZONE S
LODORE ROAD (EAST) ZONE S
LONG BEACH ROAD ZONE X
LONGS ROAD ZONE W
LOVATT ROAD ZONE W
LUCAS ROAD ZONE T
LUDBROOKS ROAD ZONE T
LUDBROOKS ROAD (LOOP) ZONE T
LYON STREET ZONE T
MACDONNELL ROAD ZONE L
MACMURRAY ROAD ZONE T
MAHINA ROAD ZONE K
MAJOR BRIDGE DRIVE ZONE X
MAKO LANE (PAIHIA) ZONE T
MANAWAORA ROAD ZONE X
MANDENO DRIVE ZONE S
MANGAKAHIA ROAD ZONE M
MANGAKARETU ROAD ZONE S
MANGAPARA ROAD (WHIRINAKI) ZONE K
MANGAPUPU ROAD ZONE K
MANGATARAIRE ROAD ZONE L
MANGATAWA ROAD ZONE N
MANGATOA ROAD ZONE N
MANGU ROAD ZONE W
MANNING STREET ZONE K
MANUWAI LANE ZONE R
MARAENUI DRIVE ZONE S
MARINA RISE ZONE T
MARINER STREET ZONE K
MARINO PLACE ZONE M
MARLOW ROAD ZONE W
MARMON STREET (EAST) ZONE K
MARMON STREET (WEST) ZONE K
MAROMAKU SCHOOL ROAD ZONE W
MAROMAKU-TOWAI ROAD ZONE W
MARSDEN PLACE (KERIKERI) ZONE S
MARSDEN ROAD (PAIHIA) ZONE T
MARSHALL ROAD ZONE T
MARSHALL STREET (MOEREWA) ZONE T
MARTIN ROAD ZONE J
MARTIN ROAD (POKERE) ZONE W
MASON AVENUE (MOEREWA) ZONE T
MASONIC LANE ZONE S
MASONS ROAD ZONE W
MASSEY STREET ZONE T
MATAUWHI ROAD ZONE X
MATAWAIA-MAROMAKU ROAD ZONE W
MATENE ROAD ZONE P
MAWSON AVENUE ZONE R
MCCAUGHAN ROAD ZONE R
MCDONALDS ROAD (OROMAHOE) ZONE T
MCDONELL STREET ZONE K
MCFARLANE STREET (NORTH) ZONE T
MCFARLANE STREET (SOUTH) ZONE T
MCINTYRES ROAD ZONE T
MCKENZIE ROAD (PURERUA) ZONE S
MCLEOD ROAD ZONE S
MEMORIAL AVENUE ZONE M
MICHIE STREET ZONE M
MIHI ROAD ZONE M
MIHIRATA ROAD ZONE W
MILL LANE ZONE S
MILL ROAD ZONE T
MIRO AVENUE ZONE J
MISSION OAK ROAD ZONE L
MISSION ROAD (KERIKERI) ZONE S
MITCHELL ROAD ZONE J
MOANA AVENUE ZONE T
MOEHAU ROAD ZONE L
MONTROSE ROAD ZONE S
MONUMENT ROAD ZONE W
MONUMENT ROAD (KAIKOHE) ZONE M
MOORING CLOSE ZONE S
MORGANS ROAD ZONE W
MOTUKIORE ROAD ZONE L
MOTUTOA ROAD ZONE K
MOUNTAIN ROAD ZONE K
MUDGWAY ROAD ZONE M
NAUTICAL DRIVE ZONE T
NELSONS ROAD ZONE W
NESS ROAD ZONE R
NEUMAN STREET (SH 11 KAWAKAWA) ZONE T
NEWTON ROAD ZONE J
NEWTON WATTS DRIVE ZONE S
NGAHUHU ROAD ZONE T
NGAPIPITO ROAD ZONE M
NGAPUA PLACE ZONE M
NGAPUHI ROAD ZONE R
NGAPUHI ROAD (KAIKOHE) ZONE M
NGAWHA SCHOOL ROAD ZONE M
NGAWHA SPRINGS ROAD ZONE M
NGAWHITU ROAD ZONE T
NIMMO STREET (CENTRAL) ZONE K
NIMMO STREET (EAST) ZONE K
NIMMO STREET (WEST) ZONE K
NINIHI ROAD ZONE N
NISBET STREET ZONE T
NORFOLK PLACE ZONE S
NORTH ROAD (SH 11 KAWAKAWA) ZONE T
NOVA STREET ZONE M
NOY ROAD ZONE T
OAKRIDGE DRIVE ZONE S
OETZMAN ROAD ZONE W
OHARA STREET ZONE M
OHURI ROAD ZONE K
OIHI ROAD ZONE S
OKAIHAU ROAD ZONE M
OKAKA ROAD ZONE L
OKIATO ROAD ZONE X
OKOKAKO ROAD ZONE S
OKORO ROAD ZONE M
OKURA DRIVE ZONE S
OLD BAY ROAD ZONE M
OLD NORTH ROAD ZONE T
OLD NORTH ROAD EXTENSION ZONE T
OLD VALLEY ROAD ZONE M
OLD WHANGAE ROAD ZONE T
OMANAIA ROAD ZONE K
OMANAIA SCHOOL ROAD ZONE K
OMAPERE ROAD ZONE M
ONEKURA ROAD ZONE R
ONEROA ROAD ZONE X
OPAHI STATION ROAD ZONE W
OPARA ROAD ZONE K
OPITO BAY ROAD ZONE S
ORAKAU ROAD ZONE P
ORANGEWOOD LANE ZONE R
ORCHARD ROAD (HARURU FALLS) ZONE T
ORCHARD ROAD (KAPIRO) ZONE S
ORIPIRO ROAD ZONE S
ORIRA ROAD ZONE M
ORMONDE PLACE ZONE M
OROMAHOE ROAD ZONE T
OROMAHOE SCHOOL ROAD ZONE T
ORRS ROAD ZONE M
OSBOURNE ROAD ZONE T
OTAENGA ROAD ZONE P
OTAERE ROAD ZONE M
OTAHA ROAD ZONE S
OTAHI ROAD ZONE K
OTAMARUA ROAD ZONE X
OTATARA MARAE ROAD ZONE L
OTAUA ROAD ZONE N
OTIRIA ROAD ZONE T
OWAE ROAD ZONE T
PA ROAD ZONE S
PACKERS ROAD ZONE T
PAIAKA ROAD ZONE W
PAKANAE CEMETERY ROAD ZONE J
PAKARU ROAD ZONE T
PAKEHAUA ROAD ZONE X
PALM DRIVE ZONE S
PANIORA ROAD ZONE J
PANORAMA ROAD ZONE T
PARAHA ROAD ZONE W
PAREMATA ROAD ZONE M
PARETU DRIVE ZONE S
PARK ROAD ZONE M
PARKERS ROAD ZONE N
PARNELL STREET ZONE K
PAROA ROAD ZONE X
PARROT ROAD ZONE N
PEACOCK GARDEN DRIVE ZONE S
PEACOCK GARDEN DRIVE EXTENSION ZONE S
PEMBROKE STREET ZONE T
PENNEY CRESCENT (KAIKOHE) ZONE M
PENNEY STREET (OPUA) ZONE T
PERAS ROAD ZONE L
PERI ROAD ZONE W
PERRY ROAD ZONE M
PICADILLY ROAD ZONE P
PICKMERE LANE ZONE S
PINE HILL ROAD ZONE J
PINEHILL ROAD ZONE T
PIONEERS WALK ZONE J
PIPIROA ROAD ZONE X
PIPIWAI ROAD ZONE W
PITT STREET ZONE X
PLUNKET STREET ZONE T
POIETE ROAD ZONE M
POINT VERONICA DRIVE ZONE T
POINT VERONICA DRIVE EXTENSION ZONE T
POKAPU ROAD ZONE T
POKAS ROAD ZONE J
POKERE ROAD ZONE W
POMARE ROAD ZONE X
POPLAR LANE ZONE S
POROTU ROAD ZONE T
POUNAMU PLACE ZONE S
PROSPECT STREET ZONE X
PUHA ROAD ZONE L
PUHITIA ROAD ZONE W
PUIA ROAD ZONE M
PUKAWA ROAD (WHIRINAKI) ZONE K
PUKEPOTO ROAD (OKAIHAU) ZONE M
PUKETI ROAD ZONE M
PUKETIRO PLACE ZONE T
PUKETONA ROAD ZONE T
PUKETOTARA ROAD ZONE S
PUKETUTU DRIVE ZONE T
PUKEWHAO ROAD ZONE L
PUKEWHAU ROAD ZONE S
PUNAKITERE LOOP ROAD ZONE N
PUNGAERE ROAD ZONE R
PURDY STREET ZONE M
PURERUA ROAD ZONE R
QUARRY ROAD (KAIKOHE) ZONE M
QUEEN STREET (KAWAKAWA) (SH 1) ZONE T
QUEEN STREET (RUSSELL) ZONE X
QUEENS VIEW ROAD ZONE X
QUINCES LANDING ZONE S
RAHIRI SETTLEMENT ROAD ZONE M
RAIHARA STREET ZONE M
RAINBOW FALLS ROAD ZONE S
RAKAUTAO ROAD ZONE M
RAKAUWAHIA ROAD ZONE M
RAMSEY ROAD ZONE L
RANFURLY STREET ZONE T
RANGE ROAD ZONE T
RANGIAHUA ROAD ZONE M
RANGIHAMAMA ROAD ZONE M
RANGIHOUA ROAD ZONE S
RANGITANE LOOP ROAD ZONE S
RANGITANE LOOP ROAD EXTENSION ZONE S
RANGITANE ROAD ZONE S
RANKIN STREET ZONE M
RANUI AVENUE ZONE S
RANUI ROAD ZONE T
RAPARAPA ROAD ZONE P
RARERE TERRACE ZONE S
RATA TIPENE ROAD ZONE W
RAWENE ROAD ZONE K
RAWHITI ROAD (NORTH) ZONE X
RAWHITI ROAD (SOUTH) ZONE X
RAYMOND STREET ZONE T
RAYNER STREET ZONE T
RECREATION ROAD ZONE M
REDCLIFFS ROAD ZONE S
REED STREET (MOEREWA) ZONE T
REINGA ROAD ZONE S
REMUERA SETTLEMENT ROAD ZONE M
RENWICK ROAD ZONE N
RESERVOIR ROAD ZONE M
RETREAT ROAD ZONE T
REWA PLACE ZONE X
RICHARDSON STREET ZONE T
RICHARDSON STREET (WEST) ZONE T
RIDDELL ROAD ZONE S
RIGDEN ROAD ZONE T
RIMU PLACE ZONE M
RIPI STREET ZONE M
RIVER DRIVE ROAD ZONE S
RIVERSTREAM DRIVE ZONE R
RIVERVIEW ROAD ZONE S
ROBERTSON STREET ZONE X
RODGER ROAD ZONE T
ROGER ROAD ZONE N
ROSELLA DRIVE ZONE T
ROSS STREET ZONE T
ROUTLEY AVENUE ZONE M
ROWSELL HEIGHTS ZONE M
ROWSELL LANE ZONE S
RUAPEKAPEKA ROAD ZONE T
RUSK ROAD ZONE W
RUSSEK ROAD ZONE W
RUSSELL ESPLANADE ZONE K
RUSSELL HEIGHTS ZONE X
RUSSELL-WHAKAPARA ROAD ZONE X
SAIES ROAD ZONE T
SAMMAREE PLACE ZONE S
SANDYS ROAD ZONE S
SAWARD ROAD ZONE M
SCHOOL ROAD (PAIHIA) ZONE T
SCORESBY STREET ZONE T
SCOTTS ROAD ZONE M
SEAVIEW HEIGHTS ROAD ZONE T
SEAVIEW ROAD (PAIHIA) ZONE T
SELWYN PLACE (KERIKERI) ZONE S
SELWYN ROAD (PAIHIA) ZONE T
SERVICE LANE #1 (KAIKOHE) ZONE M
SERVICE LANE #2 (KAIKOHE) ZONE M
SETTLEMENT ROAD ZONE T
SETTLERS WAY ZONE M
SHAW STREET ZONE M
SHEPHERDS ROAD (KERIKERI) ZONE S
SHEPHERDS ROAD (SOUTH) ZONE S
SHIRLEY ROAD ZONE R
SHOWGROUND ROAD ZONE R
SIGNAL STATION ROAD ZONE J
SIGNALS ROAD ZONE M
SILKWOOD LANE ZONE S
SIR GEORGE BACK STREET ZONE T
SIR JAMES HENARE PLACE ZONE T
SIR WILLIAM HALE CRESCENT ZONE T
SKUDDERS BEACH ROAD ZONE S
SMEATH ROAD (HUPARA) ZONE T
SMEATH ROAD (KAWAKAWA) ZONE T
SMITH CAMP ROAD ZONE T
SMITH GRAY ROAD ZONE X
SMITH ROAD (MOEREWA) ZONE T
SMOOTHY ROAD ZONE J
SNOWDON AVENUE ZONE T
SOMERVILLE ROAD ZONE R
SOUTHVIEW PLACE ZONE M
SPINNAKER POINT ZONE S
SQUIRES LANE ZONE M
ST ANDREWS PLACE ZONE S
STANNERS ROAD ZONE S
STATE HIGHWAY 1 (KAWAKAWA) ZONE T
STATE HIGHWAY 1 (MOEREWA) ZONE T
STATE HIGHWAY 1 (OHAEAWAI) ZONE M
STATE HIGHWAY 1 (OKAIHAU) ZONE M
STATE HIGHWAY 12 (OHAEAWAI) ZONE M
STATE HIGHWAY 12 (OPONONI) ZONE J
STATE HIGHWAY 12 (WAIMAMUKU) ZONE J
STATION ROAD (KAIKOHE) ZONE M
STATION ROAD (KAWAKAWA) ZONE T
STATION ROAD (MOEREWA) ZONE T
STELLA DRIVE (EAST) ZONE S
STELLA DRIVE (WEST) ZONE S
STEWARDS ROAD ZONE N
STURGE ROAD ZONE M
SULLIVAN ROAD EXTENSION ZONE T
SULLIVANS ROAD ZONE T
SYDNEY STREET ZONE M
TAHEKE ROAD ZONE L
TAHEKE ROAD (SH 12 KAIKOHE) ZONE M
TAHIWI ROAD ZONE W
TAHUNA ROAD (PAIHIA) ZONE T
TAIKIRAU ROAD ZONE W
TAITA ROAD ZONE J
TAKOU BAY ROAD ZONE S
TANA ROAD ZONE T
TANIKAHA LANE ZONE R
TAPEKA ROAD ZONE X
TAPUHI ROAD ZONE W
TARAIRE STREET (KAIKOHE) ZONE M
TARAKIHI ROAD ZONE T
TARUTARU LANE ZONE S
TASMAN PLACE ZONE S
TAU HENARE DRIVE ZONE T
TAUMATA CLOSE ZONE T
TAUMATAMAKUKU CRESCENT ZONE T
TAUMATAMAKUKU ROAD ZONE T
TAUMATAWIWI STREET ZONE J
TAWA STREET ZONE M
TAWANUI ROAD ZONE M
TAWATA ROAD ZONE N
TE AHU AHU ROAD ZONE R
TE HAUMI DRIVE ZONE T
TE HUNOKE ROAD ZONE J
TE IRENGA ROAD ZONE P
TE IRENGA WEST ROAD ZONE P
TE KAHU STREET ZONE T
TE KARUWHA PARADE ZONE T
TE KEMARA AVENUE ZONE T
TE KOWHAI POINT ROAD ZONE S
TE MAORI ROAD ZONE R
TE OHU ROAD ZONE K
TE ORO ROAD ZONE T
TE PUA ROAD (KAIKOHE) ZONE M
TE RA PLACE ZONE M
TE RA ROAD ZONE S
TE RA ROAD EXTENSION ZONE S
TE RANGI CROSS ZONE T
TE TII ROAD ZONE S
TE TII ROAD EXTENSION ZONE S
TE TIO ROAD ZONE M
TE WAHAPU ROAD ZONE X
TE WAIAROHIA ROAD ZONE J
TENNYSON STREET (EAST) ZONE M
TENNYSON STREET (WEST) ZONE M
THE ANCHORAGE ZONE S
THE ANCHORAGE EAST ZONE S
THE LOOKOUT ZONE S
THE STRAND (NORTH) ZONE X
THE STRAND (SOUTH) ZONE X
THORPE ROAD ZONE M
TIKORANGI ROAD ZONE S
TIPENE ROAD ZONE W
TIRAIRAKA TERRACE ZONE X
TIROHANGA ROAD ZONE T
TITORE WAY ZONE X
TOHITAPU ROAD ZONE T
TOI TRACK ZONE X
TOIA ROAD ZONE M
TOKAWHERO ROAD ZONE P
TOOTS DRIVE ZONE T
TOPPS ROAD ZONE R
TOTARA PLACE (KAIKOHE) ZONE M
TOTARA PLACE (KERIKERI) ZONE S
TUHUNA ROAD (KAIKOHE) ZONE M
TUI GROVE (PAIHIA) ZONE T
TUI PLACE (KERIKERI) ZONE S
TUI STREET (EAST) ZONE M
TUI STREET (OKAIHAU) ZONE M
TUI STREET (WEST) ZONE M
TUTAHI PLACE ZONE S
TYREE ROAD ZONE S
UMAWERA SCHOOL ROAD ZONE M
UPOKORAU ROAD ZONE R
URUTAWA DRIVE ZONE S
URUTI ROAD ZONE X
VALENCIA LANE ZONE S
VERONICA STREET ZONE T
VIEW ROAD ZONE J
VOGEL STREET ZONE T
VUJCICH ROAD ZONE K
WAHAMITI CEMETERY ROAD ZONE T
WAIANGA PLACE ZONE J
WAIARE ROAD ZONE R
WAIARUHE WAY ZONE X
WAIHOTA ROAD ZONE J
WAIHUKA ROAD ZONE J
WAIKARAMU ROAD ZONE M
WAIKARE ROAD ZONE T
WAIKARE VALLEY ROAD ZONE X
WAIKERIKERI ROAD ZONE L
WAIKERIKERI ROAD EXTENSION ZONE L
WAIKINO ROAD ZONE T
WAIKUKU ROAD ZONE R
WAIMA SCHOOL ROAD ZONE L
WAIMA VALLEY ROAD ZONE L
WAIMAMAKU BEACH ROAD ZONE J
WAIMANGARO ROAD ZONE T
WAIMATE NORTH ROAD ZONE S
WAIMATENUI / MATARAUA ROAD ZONE M
WAIOHANGA ROAD ZONE M
WAIOMIO ROAD (KAWAKAWA) ZONE T
WAIOMIO ROAD (WAIOMIO) ZONE T
WAIONE ROAD ZONE K
WAIOTEMARAMA GORGE ROAD ZONE J
WAIOTU ROAD ZONE W
WAIPAPA INDUSTRIAL ZONE R
WAIPAPA LANDING PLACE ZONE S
WAIPAPA LOOP ROAD ZONE R
WAIPAPA ROAD ZONE R
WAIPAPA WEST ROAD ZONE R
WAIPUNA PLACE ZONE T
WAITAHEKE ROAD ZONE M
WAITOTARA DRIVE ZONE S
WAKELIN ROAD ZONE S
WALLIS ROAD ZONE M
WAOKU ROAD ZONE L
WARD DRIVE ZONE T
WARD DRIVE (EAST) ZONE T
WATERS LANE ZONE S
WATERVIEW ZONE T
WEBSTER STREET ZONE K
WEHIRUA ROAD ZONE M
WEKAWEKA ROAD ZONE J
WELLINGTON STREET ZONE X
WELLSFORD ROAD ZONE K
WENDYWOOD LANE ZONE S
WENTWORTH TERRACE ZONE S
WHAAKAURU VALLEY ROAD ZONE X
WHAKATAHA ROAD ZONE R
WHANGAE ROAD ZONE R
WHANGARURU NORTH ROAD ZONE X
WHARAU ROAD ZONE S
WHAREKAWA ROAD ZONE K
WHARENGAERE ROAD ZONE S
WHAREPUNGA ROAD ZONE N
WHARF ROAD (HARURU FALLS) ZONE T
WHARF ROAD (OPONONI) ZONE J
WHIRINAKI SCHOOL ROAD ZONE K
WHITE ROAD (RANGIAHUA) ZONE M
WHITEMANS ROAD ZONE T
WHIU ROAD ZONE N
WIHONGI STREET ZONE M
WIKAIRAS ROAD ZONE K
WILLIAMS AVENUE (KAIKOHE) ZONE M
WILLIAMS ROAD ZONE T
WILLIAMS STREET (KAWAKAWA) ZONE T
WILLIAMS STREET (MOEREWA) ZONE T
WILLOW PARK PLACE ZONE M
WILLOWBROOK STREET ZONE T
WILSON ROAD ZONE T
WINDSOR ROAD ZONE M
WIROA ROAD ZONE S
WITANA ROAD ZONE M
WOOD STREET ZONE M
WOODBINE ROAD (KAIKOHE) ZONE M
WOODLEY DRIVE ZONE S
WOODLEY PLACE ZONE T
WRIGHTSONS ROAD ZONE R
WYNYARD STREET (KAWAKAWA) ZONE T
WYNYARD STREET (MOEREWA) ZONE T
YACHT DRIVE (OPITO BAY) ZONE S
YORK STREET ZONE X
YORKE ROAD ZONE T
YORKE ROAD (EAST) ZONE T
YOUNGS ROAD ZONE N

## Far North
Situation Report | [6 empty] | Name of Event: | Severe Weather Warning - 24/25 July 22
Local Authority Area: |  |  |  | Far North District Council
SitRep No. |  | 3 |  | (ref Page 235 Section SI02 - Incident Response)
Date: | 2022-07-25
Time: | 4PM |  |  | ( Daily SitReps due before 8am, 12noon and 4pm - or as agreed with the NTA Engineer's Rep)
Contract Area | Road Name | Route Position | Side | Site location description (eg. Xkm past Y road) | Date reported | Time | Source of Info (Contractor, call centre, public etc) | ROAD STATUS (see column 'w' notes) | Road Damage (see column 'v' notes) | RFS | RAMM Dispatch ID | Action Taken | Estimated Outage | Any planned action required | Date Resolved | Time Resolved | Additional Notes and Comments
North | MANGATOETOE ROAD (1936) | 5 | Both | 50 Mangatoetoe | 2022-07-25 | 8.00am | Call Centre | Road Open | Fallen Tree | 55319 | Set up tmp and clear tree | 4 Hours | We have to go back to remove the tree from the side of te road | 2022-07-25 | 2,00pm | Tree has been removed to the side of the road
North | KOHUMARU ROAD (1862) | 924 | Both | 924 Kohumaru Road | 2022-07-25 | 9.00am | Call Centre | Road Closed | Landslide - Overslip | 55321 | Set up tmp and close the road | 24 Hours | Set up TMP to close that section of road |  |  | To dangerous to clear slip today.will clear tommorow | Cars Can Still Get Around On Berm
North | DUNCAN ROAD (KAINGAROA) (1656) | 1329 | LHS | 1329 Duncan Road | 2022-07-25 | 9.45am | Contractor | Road Open | Fallen Tree | 55320 | Send Crew To Clear tree | 2 Hours |  | 2022-07-25 | 12.00pm | Tree has been removed | RFS 4097397 Large Pine Need Digger Assist
North | KAIMAUMAU ROAD (1838) | 546 | RHS | 546 Kaimaumau Road | 2022-07-25 | 9.45 am | Roading Staff | Road Open | Fallen Tree | 55324 | Send crew to clear tree | 2 Hours |  | 2022-07-25 | 12.00pm | Member of the public has cleared the tree | RFS 4097390 Need To Chip Slash
North | KAITAIA-AWAROA ROAD (2598) | 1606 | RHS | 1606 Kaitaia-awaroa Road | 2022-07-25 | 1.00pm | Public | One Lane Only | Fallen Tree | 55337 | Send crew to clear tree | 4hours |  | 2022-07-25 | 3.30pm | Cleared road need to go back and clear the shoulder | RF 4097342
North | PAPONGA ROAD (2129) | 1299 | Both | 1299 Paponga Road | 2022-07-25 | 2.00pm | Public | Road Closed | Fallen Tree | 55336 | Send Crew to Sign Up and try to remove | 6 Hours | May need digger to remove tomorrow
North | TAKAHUE ROAD (2371) | 588 | LHS | 588 Takahue Road | 2022-07-25 | 2.30pm | Public | One Lane Only | Landslide - Overslip | 55338 | Sent Crew To Sign UP | 24 Hours | Clear Lane Tomorrow
North | WHANGAROA ROAD (2557) | 2 | RHS | 2 Whangaroa Road | 2022-07-25 | 2.30pm | Public | One Lane Only | Landslide - Overslip | 55340 | Sent Crew To Sign Up for the night | 24 Hours | Clear Lane Tomorrow |  |  |  | RFS 4097287
North | CHURCH ROAD (KAITAIA) (1596) | 28 | RHS | 28 Church Road | 2022-07-25 | 1.30pm | Contractor | Road Passable - Caution Required | Flooding | 55342 | Crew Cleared out culverts | 2 Hours |  | 2022-07-25 | 2.30pm |  | RFS 4097380 Still Need To Chip Slash
South | RANGIHAMAMA ROAD (2226) | TBC | Centre |  | 2022-07-25 | 11.30AM | Contractor | Road Open | Fallen Tree |  | Contractors cleared fallen tree | open |  | 2022-07-25 | 10am |  | RFS 4097405 will add dispatch after talk with crew
South | UPOKORAU ROAD (2471) | 1300 | Centre |  | 2022-07-25 | 11.30AM | Call Centre | Road Closed | Fallen Tree |  | Contractors on site to clear. Tree is large. Grandaddy pine to be cleared by Northland treeworks | closed |  |  |  |  | RFS 4097358 will add dispatch after talk with crew
South | UPOKORAU ROAD (2471) | 1000 | Centre |  | 2022-07-25 | 1:30PM | Call Centre | Road Closed | Landslide - Overslip |  | Happened while on site nearing starting the tree removal further down the road. | closed |  |  |  |  | RFS 4097340 Go Back and Clean Road
South | WAIKARE ROAD (2491) | TBC | Centre |  | 2022-07-25 | 12:12PM | Contractor |  | Fallen Tree |  | Graham is heading to site now to drag out of the way | closed
South | MANAWAORA ROAD (1924) | TBC | Centre |  | 2022-07-25 | 11:45AM | Call Centre | Road Passable - Caution Required | Fallen Tree |  |  | open |  |  |  |  | RFS 4097400 Tree has fallen on half of the road Fulton Hogan accepted customer has cleared road no action requitred.
South | WAIMATE NORTH ROAD (2500) | TBC | Centre |  | 2022-07-25 | 9:00AM | Contractor | Road Passable - Caution Required | Flooding |  | Signs placed by Sharon at 9:00AM | open |  |  |  |  | RFS 4097350 Customer has cut back some of the tree and there are still work to do.
South | OLD BAY ROAD (2068) | TBC | Centre |  | 2022-07-25 | 7:13AM | Contractor | Road Passable - Caution Required | Fallen Tree |  | James cleared the tree | open |  | 2022-07-25 | 8am |  | RFS 4097368
South | WAIKARE ROAD (2491) | 1650 | LHS |  | 2022-07-25 | 1:05PM | Contractor | One Lane Only | Fallen Tree |  | Graham viewed at 1pm. | open |  |  |  |  | RFS 4097364 On private property
South | WAIKARE ROAD (2491) | 6710 | Both |  | 2022-07-25 | 1:28PM | Contractor | Road Passable - Caution Required | Flooding |  | Graham viewed at 1:28pm | open |  |  |  |  | RFS 4097283 On private property
South | SIGNALS ROAD (2313) |  |  | Between 23-33 Signals Rd | 2022-07-25 |  | Contractor
South | WAIARE ROAD (2484) | 28180 | RHS |  | 2022-07-25 | 3.01PM | Contractor | Road Open | Dropout - Underslip |  | Inspected by Bruce, made safe (pictures in email) | open
South | TAHEKE ROAD (2359) | 12299 | LHS |  | 2022-07-25 | 10.00AM | Call Centre | One Lane Only | Dropout - Underslip | 101061 | Existing dropout - minor movement reported by member of public. Inspected, EMP's adjusted and signage checked | open
|  |  |  | Channel Sweep - some roads |  |  |  |  | Other Debris Hazard
Inspectors
traffic control costs x 2 crews
CAUSEWAY ROAD ZONE T
CHAPEL STREET ZONE X
CHARLOTTE KEMP DRIVE ZONE S
CHERRINGTON ROAD ZONE T
CHURCH STREET (KAWAKAWA) ZONE T
CHURCH STREET (RUSSELL) ZONE X
CLARK ROAD (KERIKERI) ZONE S
CLASSEN ROAD ZONE K
CLENDON ESPLANADE ZONE K
CLIFFORD STREET ZONE M
COBHAM COURT ZONE S
COBHAM ROAD ZONE S
COCHRANE DRIVE ZONE R
COMMERCIAL STREET ZONE T
CONIFER LANE ZONE S
COOK ROAD ZONE M
COOKSON ROAD ZONE T
COTTLE HILL DRIVE ZONE S
COURTHOUSE LANE ZONE R
COUTTS AVENUE ZONE T
CROWN CRESCENT ZONE M
CUMBER ROAD ZONE M
CUMBER ROAD SIDE ROAD ZONE M
CURTIS ROAD ZONE K
DAROUX DRIVE ZONE R
DARWIN ROAD ZONE S
DAVIS CRESCENT (PAIHIA) ZONE T
DAVIS ROAD ZONE T
DAVIS STRONGMAN DRIVE ZONE S
DAVY ROAD ZONE T
DE HAVEN STREET ZONE T
DE MERLE STREET ZONE M
DE THIERRY STREET ZONE K
DEEMING ROAD ZONE X
DERRICK ROAD EXTENSION ZONE T
DERRICK ROAD ZONE T
DIAMOND ROAD ZONE J
DICKESON STREET ZONE M
DOELS ROAD (KAWAKAWA) ZONE T
DOMAIN ROAD ZONE T
DONALDSON ROAD ZONE M
DOONSIDE ROAD ZONE S
DOVES BAY ROAD ZONE S
DU FRESNE PLACE ZONE X
DU FRESNE PLACE EXTENSION ZONE X
DUDDY ROAD ZONE K
EDKINS ROAD (KERIKERI) ZONE S
EDMONDS ROAD ZONE S
ENGLISH BAY ROAD ZONE T
ENTERPRISE STREET ZONE M
EQUESTRIAN ZONE S
FACTORY ROAD ZONE T
FAIRLIE CRESCENT ZONE J
FAIRVIEW ROAD ZONE M
FAIRWAY DRIVE ZONE S
FALLS VIEW ROAD ZONE T
FLAGSTAFF HILL ZONE X
FLORENCE AVENUE ZONE X
FORDS ROAD ZONE W
FOREST ROAD ZONE M
FORREST HEIGHT ROAD ZONE S
FRANKLIN STREET ZONE T
FRASER ROAD ZONE T
FREESE PARK ROAD ZONE J
FULLER PLACE (KAIKOHE) ZONE M
FULLER TERRACE (KERIKERI) ZONE S
FURNESS ROAD ZONE S
GAMMONS ROAD ZONE P
GARDEN COURT ZONE T
GENERAL GATES AVENUE ZONE S
GERRARD ROAD ZONE P
GILBERT MAIR RISE ZONE X
GILES ROAD ZONE L
GILLIES ROAD (SH 1 KAWAKAWA) ZONE T
GILLIES STREET (EAST) ZONE T
GILLIES STREET (WEST) ZONE T
GILLS DRIVE (KAWAKAWA) ZONE T
GOFFE DRIVE ZONE T
GOFFE DRIVE RESERVE EXTENSION ZONE T
GOLF VIEW ROAD ZONE S
GOODWINS ROAD ZONE J
GOULD STREET ZONE X
GRAHAM ROAD ZONE N
GREEN LANE ZONE R
GREEN LANE EXTENSION ZONE R
GREENACRES DRIVE ZONE T
GREENWAY DRIVE ZONE S
GREY STREET (KAWAKAWA) ZONE T
GREYS LANE ZONE T
GROVE ROAD ZONE M
GUERIN STREET ZONE M
GUNDRY STREET ZONE K
GUTHRIE ROAD ZONE L
GUY ROAD (SH 12 KAIKOHE) ZONE M
HAILES ROAD ZONE W
HALL ROAD ZONE S
HALYARD LOOP ZONE T
HAMBLIN STREET ZONE K
HANNAH PLACE ZONE S
HANSEN ROAD (PURERUA) ZONE S
HANSEN ROAD (WAIMAMAKU) ZONE J
HAPANGA ROAD ZONE L
HAPPY VALLEY ROAD ZONE M
HARIRU ROAD ZONE R
HAROLD AVENUE ZONE M
HARRIS ROAD ZONE M
HARRISON ROAD ZONE M
HARRY'S PLACE ZONE T
HARURU FALLS ROAD ZONE T
HAUTAPU ROAD ZONE T
HAWKE DRIVE ZONE T
HAWKINS CRESCENT ZONE S
HAY ROAD ZONE T
HAZARD STREET ZONE X
HEKE STREET ZONE M
HENARE ROAD ZONE W
HERBERT ROAD (WAIARE) ZONE R
HERON HILL ZONE S
HEWITTS ROAD ZONE S
HIHITAHI RISE ZONE T
HIKUWAI ROAD ZONE X
HILLCREST ROAD (KAIKOHE) ZONE M
HIVES ROAD ZONE K
HOBSON ROAD (KERIKERI) ZONE S
HOBSON ROAD (OHAEWAI) ZONE M
HOMESTEAD ROAD ZONE S
HONE HEKE ROAD ZONE S
HONEY STREET ZONE K
HONGI STREET ZONE M
HOOKS AND HALLS ROAD ZONE J
HOPE AVENUE ZONE X
HORAHORA HEADS ROAD ZONE W
HOREKE ROAD ZONE L
HOSPITAL ROAD (KAWAKAWA) ZONE T
HULME DRIVE ZONE M
HUPARA ROAD ZONE T
HUPARA ROAD (EAST) ZONE T
IMMS ROAD (LAKE OMAPERE) ZONE M
INKSTERS ROAD ZONE W
IRONBARK ROAD ZONE R
JACARANDA PLACE ZONE S
JACKS BAY ROAD ZONE X
JACKSON ROAD ZONE K
JAMES CLENDON PLACE ZONE X
JAMES KEMP PLACE ZONE S
JAMES MCKENZIE WAY ZONE M
JAMES ROAD (MATAWAIA) ZONE W
JAMES STREET (RUSSELL) ZONE X
JAMIESON ROAD (RAWENE) ZONE K
JENKINS ROAD ZONE R
JENNINGS ROAD ZONE R
JOHNSON LANE ZONE T
JOHNSON ROAD (KAWAKAWA) ZONE T
JORDAN ROAD ZONE M
JOYCES ROAD ZONE T
KAHA PLACE ZONE X
KAHIKATEAROA ROAD ZONE S
KAHIKATOA ROAD ZONE M
KAIPATIKI ROAD ZONE T
KAKA ROAD ZONE W
KAKAPU ROAD ZONE X
KANE STREET (EAST) ZONE T
KANE STREET (WEST) ZONE T
KAPIRO ROAD ZONE S
KARAKA DRIVE ZONE S
KARAKA ROAD ZONE M
KARETU ROAD ZONE X
KARUHIRUHI ROAD ZONE K
KAURI PLACE ZONE M
KAWAKAWA-PAIHIA ROAD (SH 11 PAIHIA) ZONE T
KELLET STREET ZONE T
KELLY ROAD ZONE J
KEMP ROAD ZONE S
KEMPTHORNE ROAD ZONE X
KENDALL ROAD ZONE S
KENNEDY STREET ZONE T
KENT STREET (RUSSELL) ZONE X
KEOGH ROAD ZONE T
KERI DOWNS ROAD ZONE S
KERIKERI GROVE ZONE S
KERIKERI INLET ROAD ZONE S
KERIKERI ROAD ZONE S
KILOUNTAIN PLACE ZONE S
KING STREET ZONE S
KINGFISHER DRIVE ZONE S
KINGFISHER ROAD ZONE X
KINGI ROAD ZONE T
KINGS ROAD ZONE T
KINGSTON PLACE ZONE S
KLINAC LANE ZONE S
KNUDSENS ROAD ZONE P
KOHEWHATA ROAD ZONE M
KOKINGA POINT ROAD ZONE X
KOKOHUIA ROAD ZONE J
KORANAE ROAD ZONE R
KOROPEWA ROAD ZONE R
KOTARE HEIGHTS ZONE S
KOTUKU ROAD ZONE S
KOUTU BEACH ROAD ZONE K
KOUTU LOOP ROAD ZONE K
KOUTU POINT ROAD ZONE K
KOWHAI AVENUE (KAIKOHE) ZONE M
KOWHAI CRESCENT (PAIHIA) ZONE T
KUPA ROAD ZONE W
KURA ROAD ZONE T
KURIPARI ROAD ZONE S
LAKE ROAD (OKAIHAU) ZONE M
LAMBERG ROAD ZONE M
LANARK ROAD ZONE S
LANDING ROAD (KERIKERI) ZONE S
LANES ROAD ZONE X
LAWN STREET ZONE M
LEAITY STREET ZONE T
LEMON GROVE ZONE R
LEONARD STREET ZONE T
LEWIS ROAD ZONE M
LICHEN GROVE ZONE X
LILLY POND LANE ZONE T
LINDVART STREET ZONE M
LITTLE QUEEN STREET ZONE X
LODORE ROAD ZONE S
LODORE ROAD (EAST) ZONE S
LONG BEACH ROAD ZONE X
LONGS ROAD ZONE W
LOVATT ROAD ZONE W
LUCAS ROAD ZONE T
LUDBROOKS ROAD ZONE T
LUDBROOKS ROAD (LOOP) ZONE T
LYON STREET ZONE T
MACDONNELL ROAD ZONE L
MACMURRAY ROAD ZONE T
MAHINA ROAD ZONE K
MAJOR BRIDGE DRIVE ZONE X
MAKO LANE (PAIHIA) ZONE T
MANAWAORA ROAD ZONE X
MANDENO DRIVE ZONE S
MANGAKAHIA ROAD ZONE M
MANGAKARETU ROAD ZONE S
MANGAPARA ROAD (WHIRINAKI) ZONE K
MANGAPUPU ROAD ZONE K
MANGATARAIRE ROAD ZONE L
MANGATAWA ROAD ZONE N
MANGATOA ROAD ZONE N
MANGU ROAD ZONE W
MANNING STREET ZONE K
MANUWAI LANE ZONE R
MARAENUI DRIVE ZONE S
MARINA RISE ZONE T
MARINER STREET ZONE K
MARINO PLACE ZONE M
MARLOW ROAD ZONE W
MARMON STREET (EAST) ZONE K
MARMON STREET (WEST) ZONE K
MAROMAKU SCHOOL ROAD ZONE W
MAROMAKU-TOWAI ROAD ZONE W
MARSDEN PLACE (KERIKERI) ZONE S
MARSDEN ROAD (PAIHIA) ZONE T
MARSHALL ROAD ZONE T
MARSHALL STREET (MOEREWA) ZONE T
MARTIN ROAD ZONE J
MARTIN ROAD (POKERE) ZONE W
MASON AVENUE (MOEREWA) ZONE T
MASONIC LANE ZONE S
MASONS ROAD ZONE W
MASSEY STREET ZONE T
MATAUWHI ROAD ZONE X
MATAWAIA-MAROMAKU ROAD ZONE W
MATENE ROAD ZONE P
MAWSON AVENUE ZONE R
MCCAUGHAN ROAD ZONE R
MCDONALDS ROAD (OROMAHOE) ZONE T
MCDONELL STREET ZONE K
MCFARLANE STREET (NORTH) ZONE T
MCFARLANE STREET (SOUTH) ZONE T
MCINTYRES ROAD ZONE T
MCKENZIE ROAD (PURERUA) ZONE S
MCLEOD ROAD ZONE S
MEMORIAL AVENUE ZONE M
MICHIE STREET ZONE M
MIHI ROAD ZONE M
MIHIRATA ROAD ZONE W
MILL LANE ZONE S
MILL ROAD ZONE T
MIRO AVENUE ZONE J
MISSION OAK ROAD ZONE L
MISSION ROAD (KERIKERI) ZONE S
MITCHELL ROAD ZONE J
MOANA AVENUE ZONE T
MOEHAU ROAD ZONE L
MONTROSE ROAD ZONE S
MONUMENT ROAD ZONE W
MONUMENT ROAD (KAIKOHE) ZONE M
MOORING CLOSE ZONE S
MORGANS ROAD ZONE W
MOTUKIORE ROAD ZONE L
MOTUTOA ROAD ZONE K
MOUNTAIN ROAD ZONE K
MUDGWAY ROAD ZONE M
NAUTICAL DRIVE ZONE T
NELSONS ROAD ZONE W
NESS ROAD ZONE R
NEUMAN STREET (SH 11 KAWAKAWA) ZONE T
NEWTON ROAD ZONE J
NEWTON WATTS DRIVE ZONE S
NGAHUHU ROAD ZONE T
NGAPIPITO ROAD ZONE M
NGAPUA PLACE ZONE M
NGAPUHI ROAD ZONE R
NGAPUHI ROAD (KAIKOHE) ZONE M
NGAWHA SCHOOL ROAD ZONE M
NGAWHA SPRINGS ROAD ZONE M
NGAWHITU ROAD ZONE T
NIMMO STREET (CENTRAL) ZONE K
NIMMO STREET (EAST) ZONE K
NIMMO STREET (WEST) ZONE K
NINIHI ROAD ZONE N
NISBET STREET ZONE T
NORFOLK PLACE ZONE S
NORTH ROAD (SH 11 KAWAKAWA) ZONE T
NOVA STREET ZONE M
NOY ROAD ZONE T
OAKRIDGE DRIVE ZONE S
OETZMAN ROAD ZONE W
OHARA STREET ZONE M
OHURI ROAD ZONE K
OIHI ROAD ZONE S
OKAIHAU ROAD ZONE M
OKAKA ROAD ZONE L
OKIATO ROAD ZONE X
OKOKAKO ROAD ZONE S
OKORO ROAD ZONE M
OKURA DRIVE ZONE S
OLD BAY ROAD ZONE M
OLD NORTH ROAD ZONE T
OLD NORTH ROAD EXTENSION ZONE T
OLD VALLEY ROAD ZONE M
OLD WHANGAE ROAD ZONE T
OMANAIA ROAD ZONE K
OMANAIA SCHOOL ROAD ZONE K
OMAPERE ROAD ZONE M
ONEKURA ROAD ZONE R
ONEROA ROAD ZONE X
OPAHI STATION ROAD ZONE W
OPARA ROAD ZONE K
OPITO BAY ROAD ZONE S
ORAKAU ROAD ZONE P
ORANGEWOOD LANE ZONE R
ORCHARD ROAD (HARURU FALLS) ZONE T
ORCHARD ROAD (KAPIRO) ZONE S
ORIPIRO ROAD ZONE S
ORIRA ROAD ZONE M
ORMONDE PLACE ZONE M
OROMAHOE ROAD ZONE T
OROMAHOE SCHOOL ROAD ZONE T
ORRS ROAD ZONE M
OSBOURNE ROAD ZONE T
OTAENGA ROAD ZONE P
OTAERE ROAD ZONE M
OTAHA ROAD ZONE S
OTAHI ROAD ZONE K
OTAMARUA ROAD ZONE X
OTATARA MARAE ROAD ZONE L
OTAUA ROAD ZONE N
OTIRIA ROAD ZONE T
OWAE ROAD ZONE T
PA ROAD ZONE S
PACKERS ROAD ZONE T
PAIAKA ROAD ZONE W
PAKANAE CEMETERY ROAD ZONE J
PAKARU ROAD ZONE T
PAKEHAUA ROAD ZONE X
PALM DRIVE ZONE S
PANIORA ROAD ZONE J
PANORAMA ROAD ZONE T
PARAHA ROAD ZONE W
PAREMATA ROAD ZONE M
PARETU DRIVE ZONE S
PARK ROAD ZONE M
PARKERS ROAD ZONE N
PARNELL STREET ZONE K
PAROA ROAD ZONE X
PARROT ROAD ZONE N
PEACOCK GARDEN DRIVE ZONE S
PEACOCK GARDEN DRIVE EXTENSION ZONE S
PEMBROKE STREET ZONE T
PENNEY CRESCENT (KAIKOHE) ZONE M
PENNEY STREET (OPUA) ZONE T
PERAS ROAD ZONE L
PERI ROAD ZONE W
PERRY ROAD ZONE M
PICADILLY ROAD ZONE P
PICKMERE LANE ZONE S
PINE HILL ROAD ZONE J
PINEHILL ROAD ZONE T
PIONEERS WALK ZONE J
PIPIROA ROAD ZONE X
PIPIWAI ROAD ZONE W
PITT STREET ZONE X
PLUNKET STREET ZONE T
POIETE ROAD ZONE M
POINT VERONICA DRIVE ZONE T
POINT VERONICA DRIVE EXTENSION ZONE T
POKAPU ROAD ZONE T
POKAS ROAD ZONE J
POKERE ROAD ZONE W
POMARE ROAD ZONE X
POPLAR LANE ZONE S
POROTU ROAD ZONE T
POUNAMU PLACE ZONE S
PROSPECT STREET ZONE X
PUHA ROAD ZONE L
PUHITIA ROAD ZONE W
PUIA ROAD ZONE M
PUKAWA ROAD (WHIRINAKI) ZONE K
PUKEPOTO ROAD (OKAIHAU) ZONE M
PUKETI ROAD ZONE M
PUKETIRO PLACE ZONE T
PUKETONA ROAD ZONE T
PUKETOTARA ROAD ZONE S
PUKETUTU DRIVE ZONE T
PUKEWHAO ROAD ZONE L
PUKEWHAU ROAD ZONE S
PUNAKITERE LOOP ROAD ZONE N
PUNGAERE ROAD ZONE R
PURDY STREET ZONE M
PURERUA ROAD ZONE R
QUARRY ROAD (KAIKOHE) ZONE M
QUEEN STREET (KAWAKAWA) (SH 1) ZONE T
QUEEN STREET (RUSSELL) ZONE X
QUEENS VIEW ROAD ZONE X
QUINCES LANDING ZONE S
RAHIRI SETTLEMENT ROAD ZONE M
RAIHARA STREET ZONE M
RAINBOW FALLS ROAD ZONE S
RAKAUTAO ROAD ZONE M
RAKAUWAHIA ROAD ZONE M
RAMSEY ROAD ZONE L
RANFURLY STREET ZONE T
RANGE ROAD ZONE T
RANGIAHUA ROAD ZONE M
RANGIHAMAMA ROAD ZONE M
RANGIHOUA ROAD ZONE S
RANGITANE LOOP ROAD ZONE S
RANGITANE LOOP ROAD EXTENSION ZONE S
RANGITANE ROAD ZONE S
RANKIN STREET ZONE M
RANUI AVENUE ZONE S
RANUI ROAD ZONE T
RAPARAPA ROAD ZONE P
RARERE TERRACE ZONE S
RATA TIPENE ROAD ZONE W
RAWENE ROAD ZONE K
RAWHITI ROAD (NORTH) ZONE X
RAWHITI ROAD (SOUTH) ZONE X
RAYMOND STREET ZONE T
RAYNER STREET ZONE T
RECREATION ROAD ZONE M
REDCLIFFS ROAD ZONE S
REED STREET (MOEREWA) ZONE T
REINGA ROAD ZONE S
REMUERA SETTLEMENT ROAD ZONE M
RENWICK ROAD ZONE N
RESERVOIR ROAD ZONE M
RETREAT ROAD ZONE T
REWA PLACE ZONE X
RICHARDSON STREET ZONE T
RICHARDSON STREET (WEST) ZONE T
RIDDELL ROAD ZONE S
RIGDEN ROAD ZONE T
RIMU PLACE ZONE M
RIPI STREET ZONE M
RIVER DRIVE ROAD ZONE S
RIVERSTREAM DRIVE ZONE R
RIVERVIEW ROAD ZONE S
ROBERTSON STREET ZONE X
RODGER ROAD ZONE T
ROGER ROAD ZONE N
ROSELLA DRIVE ZONE T
ROSS STREET ZONE T
ROUTLEY AVENUE ZONE M
ROWSELL HEIGHTS ZONE M
ROWSELL LANE ZONE S
RUAPEKAPEKA ROAD ZONE T
RUSK ROAD ZONE W
RUSSEK ROAD ZONE W
RUSSELL ESPLANADE ZONE K
RUSSELL HEIGHTS ZONE X
RUSSELL-WHAKAPARA ROAD ZONE X
SAIES ROAD ZONE T
SAMMAREE PLACE ZONE S
SANDYS ROAD ZONE S
SAWARD ROAD ZONE M
SCHOOL ROAD (PAIHIA) ZONE T
SCORESBY STREET ZONE T
SCOTTS ROAD ZONE M
SEAVIEW HEIGHTS ROAD ZONE T
SEAVIEW ROAD (PAIHIA) ZONE T
SELWYN PLACE (KERIKERI) ZONE S
SELWYN ROAD (PAIHIA) ZONE T
SERVICE LANE #1 (KAIKOHE) ZONE M
SERVICE LANE #2 (KAIKOHE) ZONE M
SETTLEMENT ROAD ZONE T
SETTLERS WAY ZONE M
SHAW STREET ZONE M
SHEPHERDS ROAD (KERIKERI) ZONE S
SHEPHERDS ROAD (SOUTH) ZONE S
SHIRLEY ROAD ZONE R
SHOWGROUND ROAD ZONE R
SIGNAL STATION ROAD ZONE J
SIGNALS ROAD ZONE M
SILKWOOD LANE ZONE S
SIR GEORGE BACK STREET ZONE T
SIR JAMES HENARE PLACE ZONE T
SIR WILLIAM HALE CRESCENT ZONE T
SKUDDERS BEACH ROAD ZONE S
SMEATH ROAD (HUPARA) ZONE T
SMEATH ROAD (KAWAKAWA) ZONE T
SMITH CAMP ROAD ZONE T
SMITH GRAY ROAD ZONE X
SMITH ROAD (MOEREWA) ZONE T
SMOOTHY ROAD ZONE J
SNOWDON AVENUE ZONE T
SOMERVILLE ROAD ZONE R
SOUTHVIEW PLACE ZONE M
SPINNAKER POINT ZONE S
SQUIRES LANE ZONE M
ST ANDREWS PLACE ZONE S
STANNERS ROAD ZONE S
STATE HIGHWAY 1 (KAWAKAWA) ZONE T
STATE HIGHWAY 1 (MOEREWA) ZONE T
STATE HIGHWAY 1 (OHAEAWAI) ZONE M
STATE HIGHWAY 1 (OKAIHAU) ZONE M
STATE HIGHWAY 12 (OHAEAWAI) ZONE M
STATE HIGHWAY 12 (OPONONI) ZONE J
STATE HIGHWAY 12 (WAIMAMUKU) ZONE J
STATION ROAD (KAIKOHE) ZONE M
STATION ROAD (KAWAKAWA) ZONE T
STATION ROAD (MOEREWA) ZONE T
STELLA DRIVE (EAST) ZONE S
STELLA DRIVE (WEST) ZONE S
STEWARDS ROAD ZONE N
STURGE ROAD ZONE M
SULLIVAN ROAD EXTENSION ZONE T
SULLIVANS ROAD ZONE T
SYDNEY STREET ZONE M
TAHEKE ROAD ZONE L
TAHEKE ROAD (SH 12 KAIKOHE) ZONE M
TAHIWI ROAD ZONE W
TAHUNA ROAD (PAIHIA) ZONE T
TAIKIRAU ROAD ZONE W
TAITA ROAD ZONE J
TAKOU BAY ROAD ZONE S
TANA ROAD ZONE T
TANIKAHA LANE ZONE R
TAPEKA ROAD ZONE X
TAPUHI ROAD ZONE W
TARAIRE STREET (KAIKOHE) ZONE M
TARAKIHI ROAD ZONE T
TARUTARU LANE ZONE S
TASMAN PLACE ZONE S
TAU HENARE DRIVE ZONE T
TAUMATA CLOSE ZONE T
TAUMATAMAKUKU CRESCENT ZONE T
TAUMATAMAKUKU ROAD ZONE T
TAUMATAWIWI STREET ZONE J
TAWA STREET ZONE M
TAWANUI ROAD ZONE M
TAWATA ROAD ZONE N
TE AHU AHU ROAD ZONE R
TE HAUMI DRIVE ZONE T
TE HUNOKE ROAD ZONE J
TE IRENGA ROAD ZONE P
TE IRENGA WEST ROAD ZONE P
TE KAHU STREET ZONE T
TE KARUWHA PARADE ZONE T
TE KEMARA AVENUE ZONE T
TE KOWHAI POINT ROAD ZONE S
TE MAORI ROAD ZONE R
TE OHU ROAD ZONE K
TE ORO ROAD ZONE T
TE PUA ROAD (KAIKOHE) ZONE M
TE RA PLACE ZONE M
TE RA ROAD ZONE S
TE RA ROAD EXTENSION ZONE S
TE RANGI CROSS ZONE T
TE TII ROAD ZONE S
TE TII ROAD EXTENSION ZONE S
TE TIO ROAD ZONE M
TE WAHAPU ROAD ZONE X
TE WAIAROHIA ROAD ZONE J
TENNYSON STREET (EAST) ZONE M
TENNYSON STREET (WEST) ZONE M
THE ANCHORAGE ZONE S
THE ANCHORAGE EAST ZONE S
THE LOOKOUT ZONE S
THE STRAND (NORTH) ZONE X
THE STRAND (SOUTH) ZONE X
THORPE ROAD ZONE M
TIKORANGI ROAD ZONE S
TIPENE ROAD ZONE W
TIRAIRAKA TERRACE ZONE X
TIROHANGA ROAD ZONE T
TITORE WAY ZONE X
TOHITAPU ROAD ZONE T
TOI TRACK ZONE X
TOIA ROAD ZONE M
TOKAWHERO ROAD ZONE P
TOOTS DRIVE ZONE T
TOPPS ROAD ZONE R
TOTARA PLACE (KAIKOHE) ZONE M
TOTARA PLACE (KERIKERI) ZONE S
TUHUNA ROAD (KAIKOHE) ZONE M
TUI GROVE (PAIHIA) ZONE T
TUI PLACE (KERIKERI) ZONE S
TUI STREET (EAST) ZONE M
TUI STREET (OKAIHAU) ZONE M
TUI STREET (WEST) ZONE M
TUTAHI PLACE ZONE S
TYREE ROAD ZONE S
UMAWERA SCHOOL ROAD ZONE M
UPOKORAU ROAD ZONE R
URUTAWA DRIVE ZONE S
URUTI ROAD ZONE X
VALENCIA LANE ZONE S
VERONICA STREET ZONE T
VIEW ROAD ZONE J
VOGEL STREET ZONE T
VUJCICH ROAD ZONE K
WAHAMITI CEMETERY ROAD ZONE T
WAIANGA PLACE ZONE J
WAIARE ROAD ZONE R
WAIARUHE WAY ZONE X
WAIHOTA ROAD ZONE J
WAIHUKA ROAD ZONE J
WAIKARAMU ROAD ZONE M
WAIKARE ROAD ZONE T
WAIKARE VALLEY ROAD ZONE X
WAIKERIKERI ROAD ZONE L
WAIKERIKERI ROAD EXTENSION ZONE L
WAIKINO ROAD ZONE T
WAIKUKU ROAD ZONE R
WAIMA SCHOOL ROAD ZONE L
WAIMA VALLEY ROAD ZONE L
WAIMAMAKU BEACH ROAD ZONE J
WAIMANGARO ROAD ZONE T
WAIMATE NORTH ROAD ZONE S
WAIMATENUI / MATARAUA ROAD ZONE M
WAIOHANGA ROAD ZONE M
WAIOMIO ROAD (KAWAKAWA) ZONE T
WAIOMIO ROAD (WAIOMIO) ZONE T
WAIONE ROAD ZONE K
WAIOTEMARAMA GORGE ROAD ZONE J
WAIOTU ROAD ZONE W
WAIPAPA INDUSTRIAL ZONE R
WAIPAPA LANDING PLACE ZONE S
WAIPAPA LOOP ROAD ZONE R
WAIPAPA ROAD ZONE R
WAIPAPA WEST ROAD ZONE R
WAIPUNA PLACE ZONE T
WAITAHEKE ROAD ZONE M
WAITOTARA DRIVE ZONE S
WAKELIN ROAD ZONE S
WALLIS ROAD ZONE M
WAOKU ROAD ZONE L
WARD DRIVE ZONE T
WARD DRIVE (EAST) ZONE T
WATERS LANE ZONE S
WATERVIEW ZONE T
WEBSTER STREET ZONE K
WEHIRUA ROAD ZONE M
WEKAWEKA ROAD ZONE J
WELLINGTON STREET ZONE X
WELLSFORD ROAD ZONE K
WENDYWOOD LANE ZONE S
WENTWORTH TERRACE ZONE S
WHAAKAURU VALLEY ROAD ZONE X
WHAKATAHA ROAD ZONE R
WHANGAE ROAD ZONE R
WHANGARURU NORTH ROAD ZONE X
WHARAU ROAD ZONE S
WHAREKAWA ROAD ZONE K
WHARENGAERE ROAD ZONE S
WHAREPUNGA ROAD ZONE N
WHARF ROAD (HARURU FALLS) ZONE T
WHARF ROAD (OPONONI) ZONE J
WHIRINAKI SCHOOL ROAD ZONE K
WHITE ROAD (RANGIAHUA) ZONE M
WHITEMANS ROAD ZONE T
WHIU ROAD ZONE N
WIHONGI STREET ZONE M
WIKAIRAS ROAD ZONE K
WILLIAMS AVENUE (KAIKOHE) ZONE M
WILLIAMS ROAD ZONE T
WILLIAMS STREET (KAWAKAWA) ZONE T
WILLIAMS STREET (MOEREWA) ZONE T
WILLOW PARK PLACE ZONE M
WILLOWBROOK STREET ZONE T
WILSON ROAD ZONE T
WINDSOR ROAD ZONE M
WIROA ROAD ZONE S
WITANA ROAD ZONE M
WOOD STREET ZONE M
WOODBINE ROAD (KAIKOHE) ZONE M
WOODLEY DRIVE ZONE S
WOODLEY PLACE ZONE T
WRIGHTSONS ROAD ZONE R
WYNYARD STREET (KAWAKAWA) ZONE T
WYNYARD STREET (MOEREWA) ZONE T
YACHT DRIVE (OPITO BAY) ZONE S
YORK STREET ZONE X
YORKE ROAD ZONE T
YORKE ROAD (EAST) ZONE T
YOUNGS ROAD ZONE N